## Sheet1
ID | Work Item Type | Iteration Path | Tags | Created Date | Changed Date | Closed Date | Title | Parent | State | Effort | Business Value | Value Area | Area Path | Product Area | Priority | Severity | Frequence | Prevalence
53436 | Epic | Main |  | 2024-03-18 11:17 | 2025-04-30 15:13 |  | EFSTA France | null | Active |  |  | F&B POS – Conqueror | Main\Teams\POS |  | 3
62270 | Feature | Main | Small Change | 2024-06-03 15:25 | 2026-02-11 12:37 |  | EFSTA France - Web Reservations | 53436 | Active |  |  | Same as parent | Main\Teams\POS |  | 3
62271 | Feature | Main | Small Change | 2024-06-03 15:25 | 2026-02-17 10:28 | 2025-01-20 10:05 | EFSTA France - Update Version | 53436 | Closed |  |  | Same as parent | Main\Teams\POS |  | 3
62272 | User Story | Main\2024-Q3\120 | Backend; Conqueror; EFSTA | 2024-06-03 15:26 | 2024-07-30 09:18 | 2024-07-30 09:18 | EFSTA - Update Version France | 62271 | Closed |  |  | Business | Main\Teams\POS |  | 2
62273 | User Story | Main\2024-Q3\120 | Backend; Conqueror; EFSTA | 2024-06-03 15:26 | 2024-07-31 09:44 | 2024-07-31 09:44 | EFSTA - Update Version Germany | 62271 | Closed |  |  | Business | Main\Teams\POS |  | 2
64728 | Feature | Main | small | 2024-07-04 14:47 | 2026-02-17 10:28 | 2025-04-30 15:05 | EFSTA France - Update 2024 | 53436 | Closed |  |  | Same as parent | Main\Teams\POS |  | 3
53440 | User Story | Main\2024-Q1\111 | Conqueror; EFSTA | 2024-03-18 11:24 | 2024-07-04 14:47 | 2024-03-18 17:32 | Controllo associazione gruppi di tasse per tariffe al lancio di Conqueror | 64728 | Closed |  |  | Business | Main\Teams\POS |  | 2
53444 | User Story | Main\2025-Q1\132 | Conqueror; EFSTA | 2024-03-18 11:29 | 2025-01-09 17:43 | 2025-01-09 17:43 | Verifica funzionalità esportazione dati fiscali su ultima versione EFR | 64728 | Closed |  |  | Business | Main\Teams\POS |  | 2
79621 | Feature | Main | Small Change | 2025-01-30 10:16 | 2026-02-11 12:37 |  | EFSTA France - Bugs | 53436 | Active |  |  | Same as parent | Main\Teams\POS |  | 3
77579 | Bug | Main | Backend; BLOCKER; Cloud; Conqueror; EFSTA; PM_Support_Needed; QA | 2025-01-07 17:29 | 2025-10-16 10:06 |  | [TS] Wrong calculation on tax | 79621 | On wait |  |  | Business | Main\Teams\POS |  | 2 | 0 – Undefined | 0 - Undefined | 0 - Undefined
79895 | Feature | Main | small | 2025-02-03 09:43 | 2026-02-17 10:28 | 2025-04-30 15:05 | EFSTA France - 2025 Requests for Compliancy | 53436 | Closed |  |  | Same as parent | Main\Teams\POS |  | 3
83625 | User Story | Main\2025-Q1\137 |  | 2025-03-18 10:54 | 2025-03-27 14:22 | 2025-03-27 14:22 | [EFSTA] check valori RN | 79895 | Closed |  |  | Business | Main\Teams\POS |  | 2
83626 | User Story | Main\2025-Q1\137 |  | 2025-03-18 10:56 | 2025-03-27 13:13 | 2025-03-27 13:13 | [EFSTA] indagare messaggio log | 79895 | Closed |  |  | Business | Main\Teams\POS |  | 2
83627 | User Story | Main\2025-Q1\137 |  | 2025-03-18 10:58 | 2025-03-27 13:11 | 2025-03-27 13:11 | [EFSTA] check RN=0 | 79895 | Closed |  |  | Business | Main\Teams\POS |  | 2
83628 | User Story | Main\2025-Q2\139 |  | 2025-03-18 11:00 | 2025-05-12 17:53 | 2025-04-23 13:45 | [EFSTA] manca l'icona dell'€ nello scontrino | 79895 | Closed |  |  | Business | Main\Teams\POS |  | 2
84326 | Bug | Main\2025-Q2\138 | Conqueror; EFSTA; QA | 2025-03-27 13:01 | 2025-04-03 15:48 | 2025-04-03 15:48 | EFSTA - Receipt error when printing Void item | 79895 | Closed |  |  | Business | Main\Products\Square\POS\Integration |  | 2 | 0 – Undefined | 0 - Undefined | 0 - Undefined
79896 | Feature | Main | small | 2025-02-03 09:45 | 2026-02-17 10:28 | 2025-04-30 15:06 | EFSTA France - Certification | 53436 | Closed |  |  | Same as parent | Main\Teams\POS |  | 3
79897 | User Story | Main\2025-Q1\135 | Backend; Design; QA | 2025-02-03 09:51 | 2025-03-14 11:44 | 2025-02-26 09:32 | Nuovo modo di stampare lo scontrino | 79896 | Closed |  |  | Business | Main\Teams\POS |  | 2
80353 | Task | Main\2025-Q1\134 |  | 2025-02-07 09:07 | 2025-02-26 11:30 | 2025-02-26 11:30 | [CQ] New receipt format | 79897 | Closed |  |  |  | Main\Teams\POS |  | 2
80354 | Task | Main\2025-Q1\134 |  | 2025-02-07 09:08 | 2025-02-07 09:08 | 2025-02-07 09:08 | [CQ] Force new format for French licenses | 79897 | Closed |  |  |  | Main\Teams\POS |  | 2
79901 | User Story | Main\2025-Q1\135 | Backend; Not ready to test yet | 2025-02-03 09:53 | 2025-02-26 11:30 | 2025-02-26 11:30 | EFSTA France - Visualizzare il Redeem come pagamento | 79896 | Closed |  |  | Business | Main\Teams\POS |  | 2
79903 | User Story | Main\2025-Q1\134 | Backend | 2025-02-03 09:57 | 2025-02-17 09:53 | 2025-02-17 09:53 | EFSTA France - Documentazione per la certificazione | 79896 | Closed |  |  | Business | Main\Teams\POS |  | 2
80293 | User Story | Main\2025-Q1\135 | Backend | 2025-02-06 11:28 | 2025-03-03 09:40 | 2025-03-03 09:40 | Supporto per Audit EFSTA 27-28 Febbraio | 79896 | Closed |  |  | Business | Main\Teams\POS |  | 2
80294 | Tech Story | Main\2025-Q1\135 | Backend | 2025-02-06 11:30 | 2025-03-03 09:40 | 2025-03-03 09:40 | Preparazione Audit EFSTA 27/28 Febbraio | 79896 | Closed |  |  |  | Main\Teams\POS
86744 | User Story | Main\2025-Q2\140 | Backend; Conqueror; EFSTA | 2025-04-23 16:12 | 2025-05-12 09:38 | 2025-05-12 09:38 | [EFSTA] Review dei documenti | 79896 | Closed |  |  | Business | Main\Teams\POS |  | 1
86745 | User Story | Main\2025-Q4\152 | Backend; Conqueror; EFSTA; QA | 2025-04-23 16:13 | 2025-11-13 15:56 | 2025-10-16 16:03 | [EFSTA] Aggiungere Informazioni certificazione NF525 nell'about del Conqueror | 79896 | Closed |  |  | Business | Main\Teams\POS |  | 1
81136 | User Story | Main\2025-Q1\135 | Backend; Conqueror | 2025-02-17 09:54 | 2025-03-03 09:53 | 2025-03-03 09:53 | EFSTA France - Documentazione word + verifiche infocert | 79896 | Closed |  |  | Business | Main\Teams\POS |  | 2
78845 | Feature | Main | Small Change | 2025-01-21 15:40 | 2026-02-11 12:37 |  | EFSTA France - QR Code | 53436 | New |  |  | Same as parent | Main\Teams\POS |  | 3
78846 | Feature | Main | Release D; Small Change | 2025-01-21 15:40 | 2026-02-17 10:28 | 2025-06-23 18:06 | EFSTA France - Documentation | 53436 | Closed |  |  | Same as parent | Main\Teams\POS |  | 3
64715 | User Story | Main\2024-Q3\119 | Backend; Conqueror; EFSTA | 2024-07-04 14:36 | 2024-07-22 17:02 | 2024-07-22 17:02 | Supporto per Deloitte con documentazione | 78846 | Closed |  |  | Business | Main\Teams\POS |  | 2
68336 | User Story | Main\2025-Q1\132 | EFSTA | 2024-09-02 16:32 | 2025-01-20 12:33 | 2025-01-20 12:33 | Documentazione certificazione Francia 1/2 | 78846 | Closed |  |  | Business | Main\Teams\POS |  | 2
78703 | User Story | Main\2025-Q1\133 |  | 2025-01-20 12:35 | 2025-02-03 09:57 | 2025-02-03 09:57 | Documentazione certificazione Francia 2/2 | 78846 | Closed |  |  | Business | Main\Teams\POS |  | 2
83624 | User Story | Main\2025-Q2\140 | Backend; Conqueror; EFSTA | 2025-03-18 10:51 | 2025-05-05 12:00 | 2025-05-05 12:00 | [EFSTA] rivedere il processo di installazione | 78846 | Closed |  |  | Business | Main\Teams\POS |  | 1
83886 | Bug | Main\2025-Q1\137 | Backend; Conqueror; QA | 2025-03-21 12:42 | 2025-04-11 10:13 | 2025-03-25 17:15 | EFSTA - Backup errato | 78846 | Closed |  |  | Business | Main\Teams\POS |  | 2 | 0 – Undefined | 0 - Undefined | 0 - Undefined
76342 | Epic | Main |  | 2024-12-09 17:01 | 2025-01-30 15:34 |  | Technical Debt for Stability and Growth | null | New |  |  | F&B POS – Partnership | Main\Products\Square\POS\Integration |  | 3
30946 | Feature | Main | Backend; ktlo; Team POS | 2023-03-07 08:51 | 2025-12-19 15:08 |  | Lavori propedeutici per il nuovo POS | 76342 | Active |  |  | Same as parent | Main\Products\Square\POS\Integration |  | 2
30886 | Tech Story | Main\2023-Q3\94 | Backend | 2023-03-06 14:00 | 2025-01-20 10:49 | 2023-08-02 11:08 | Rinomiare enum DeptType in DepartmentType in Qamf.Economical | 30946 | Closed |  |  |  | Main\Teams\POS
30887 | User Story | Main | Backend; Team POS | 2023-03-06 14:05 | 2025-11-05 14:33 |  | Finire la pulizia di ShiftControl.cpp | 30946 | New |  |  | Same as parent | Main\Products\Square\POS\Integration |  | 2
30947 | User Story | Main | Backend; Team POS | 2023-03-07 08:53 | 2025-11-05 14:33 |  | Eliminazione delle Transaction.cpp dal LaneControl | 30946 | New |  |  | Same as parent | Main\Products\Square\POS\Integration |  | 2
31400 | User Story | Main | Backend; Team POS | 2023-03-16 14:08 | 2025-11-05 14:33 |  | Eliminare CleanCash dal codice | 30946 | New |  |  | Same as parent | Main\Products\Square\POS\Integration |  | 2
50759 | Feature | Main | ktlo | 2024-02-20 12:26 | 2025-01-23 17:37 |  | Connection Square | 76342 | Active |  |  | Same as parent | Main\Products\Square\POS\Integration |  | 3
47982 | Tech Story | Main | Backend | 2024-01-12 18:59 | 2025-01-20 10:48 | 2024-02-05 15:37 | Dinamically create an url for Authorize Square pair | 50759 | Closed |  |  |  | Main\Products\Square\POS\Integration
47983 | Tech Story | Main\2024-Q1\107 | Backend; QA | 2024-01-12 19:00 | 2024-05-27 17:24 | 2024-02-05 15:37 | Square /token invocation Endpoint | 50759 | Closed |  |  |  | Main\Products\Square\POS\Integration
47984 | Tech Story | Main\2024-Q1\107 | Backend | 2024-01-12 19:16 | 2024-05-27 17:24 | 2024-01-25 15:17 | Long polling to keep-alive access token | 50759 | Closed |  |  |  | Main\Products\Square\POS\Integration
47985 | Tech Story | Main | Backend | 2024-01-12 19:17 | 2025-01-20 10:48 | 2024-02-05 15:37 | Expose access token on update | 50759 | Closed |  |  |  | Main\Products\Square\POS\Integration
47986 | Tech Story | Main\2024-Q1\107 | Backend | 2024-01-12 19:18 | 2024-05-27 17:24 | 2024-01-25 12:12 | Store Square ApplicationIds for every environment on Manifest | 50759 | Closed |  |  |  | Main\Products\Square\POS\Integration
47987 | Tech Story | Main\2024-Q1\107 | Backend | 2024-01-12 19:18 | 2024-05-27 17:24 | 2024-01-25 12:12 | Define Square Webhook subscription url | 50759 | Closed |  |  |  | Main\Products\Square\POS\Integration
47988 | Tech Story | Main | Backend | 2024-01-12 19:19 | 2025-01-20 10:48 | 2024-02-21 11:40 | Delete Previous Production webhook subscription after production release | 50759 | Closed |  |  |  | Main\Products\Square\POS\Integration
47989 | Tech Story | Main\2024-Q1\107 | Backend | 2024-01-12 19:19 | 2024-05-27 17:24 | 2024-01-25 12:13 | Create and register applications for every Qubica environment | 50759 | Closed |  |  |  | Main\Products\Square\POS\Integration
48005 | Tech Story | Main | Backend | 2024-01-14 10:35 | 2025-01-20 10:48 | 2024-02-21 10:06 | Create Pair between Center and Location | 50759 | Closed |  |  |  | Main\Products\Square\POS\Integration
48424 | Tech Story | Main\2024-Q1\107 | Backend | 2024-01-22 09:15 | 2024-05-27 17:24 | 2024-02-05 16:21 | Code Coverage for Square OAuth | 50759 | Closed |  |  |  | Main\Products\Square\POS\Integration
48425 | User Story | Main | Backend | 2024-01-22 09:15 | 2025-11-05 14:33 |  | Alert on Square Token refresh Failure | 50759 | New |  |  | Same as parent | Main\Products\Square\POS\Integration |  | 2
48426 | Tech Story | Main\2024-Q1\109 | Backend; QA | 2024-01-22 09:16 | 2024-03-27 16:42 | 2024-02-28 12:07 | Update Square Access Token into CQ Provider table | 50759 | Closed |  |  |  | Main\Teams\Payments
50929 | Issue | Main\2024-Q1\109 | Conqueror | 2024-02-20 15:28 | 2024-02-20 16:48 | 2024-02-20 16:48 | [CQ] Transaction failed | 48426 | Closed |  |  |  | Main\Teams\Payments |  | 2
48466 | User Story | Main | Backend | 2024-01-22 11:48 | 2025-11-05 14:33 |  | Encrypt & Decrypt tokens in redis & Sql Server | 50759 | New |  |  | Same as parent | Main\Products\Square\POS\Integration |  | 2
48467 | User Story | Main | Backend | 2024-01-22 11:51 | 2025-11-05 14:33 |  | Add support to revoke old access token after refresh (wait 24h) | 50759 | New |  |  | Same as parent | Main\Products\Square\POS\Integration |  | 2
48581 | User Story | Main\2024-Q1\109 | Backend; QA; Release: Connect QAMF to Square via OAuth | 2024-01-23 14:36 | 2025-01-20 10:48 | 2024-02-28 16:31 | Disconnect the QAMF Company from Square | 50759 | Closed |  |  | Business | Main\Products\Square\POS\Integration |  | 2
48625 | User Story | Main | Backend | 2024-01-23 17:58 | 2025-11-05 14:33 |  | Move endpoints not OAuth related to a different controller | 50759 | New |  |  | Same as parent | Main\Products\Square\POS\Integration |  | 2
48756 | User Story | Main | Backend POS | 2024-01-24 16:15 | 2025-11-05 14:33 |  | Debito Tecnico Square Connection - CenterPairingController | 50759 | New |  |  | Same as parent | Main\Products\Square\POS\Integration |  | 2
50196 | User Story | Main\2024-Q1\109 | Release: Connect QAMF to Square via OAuth | 2024-02-14 08:38 | 2024-05-27 17:24 | 2024-02-26 09:47 | Demo Square restaurant app + Back Office | 50759 | Closed |  |  | Business | Main\Products\Square\POS\Integration |  | 2
50197 | Tech Story | Main\2024-Q1\110 | Backend; Cloud; QA; Release: Connect QAMF to Square via OAuth | 2024-02-14 08:42 | 2025-01-20 10:48 | 2024-03-11 16:47 | Square connection for production channel - webhook | 50759 | Closed |  |  | Business | Main\Products\Square\POS\Integration |  | 2
52003 | Task | Main\2024-Q1\110 |  | 2024-03-04 12:54 | 2024-03-06 15:44 | 2024-03-06 15:44 | Redirect correctly Payments routes | 50197 | Closed |  |  |  | Main\Products\Square\POS\Integration |  | 2
52005 | Task | Main\2024-Q1\110 |  | 2024-03-04 12:58 | 2024-03-05 09:09 | 2024-03-05 09:09 | Add region & channel in CenterPairing/GetByLocationId response | 50197 | Closed |  |  |  | Main\Products\Square\POS\Integration |  | 2
52006 | Task | Main\2024-Q1\110 |  | 2024-03-04 12:59 | 2024-03-06 12:39 | 2024-03-06 12:39 | Send event in topic for Revoke Token | 50197 | Closed |  |  |  | Main\Products\Square\POS\Integration |  | 2
52007 | Task | Main\2024-Q1\110 |  | 2024-03-04 13:05 | 2024-03-06 12:50 | 2024-03-06 12:50 | Manage topic subscription handler instead of rest API in SecuritySvc | 50197 | Closed |  |  |  | Main\Products\Square\POS\Integration |  | 2
52008 | Task | Main\2024-Q1\110 |  | 2024-03-04 13:06 | 2024-03-05 16:18 | 2024-03-05 16:18 | Create Topics and subscriptions | 50197 | Closed |  |  |  | Main\Products\Square\POS\Integration |  | 2
50229 | User Story | Main\2024-Q1\109 | Backend; QA | 2024-02-14 14:22 | 2025-01-20 10:48 | 2024-02-27 12:34 | Create square webhook queue | 50759 | Closed |  |  | Business | Main\Products\Square\POS\Integration |  | 2
51467 | Issue | Main\2024-Q1\109 |  | 2024-02-27 11:34 | 2024-02-27 11:34 |  | Exceptions after device.code.paired | 50229 | ToDo |  |  |  | Main\Products\Square\POS\Integration |  | 2
50268 | Tech Story | Main\2024-Q3\119 | Backend; Cloud; Frontend; QA | 2024-02-15 08:45 | 2025-01-20 10:49 | 2024-07-11 14:52 | [QPortal] Square add Location ID to center-list route | 50759 | Closed |  |  |  | Main\Products\Square\POS\Integration
50274 | Task | Main |  | 2024-02-15 09:32 | 2024-06-13 17:49 | 2024-06-13 17:49 | [FE] Rimuovere la chiamata get-by-id per ogni centro | 50268 | Closed |  |  |  | Main\Products\POS Partners\POS |  | 2
50275 | Task | Main |  | 2024-02-15 09:33 | 2024-07-10 11:51 | 2024-07-10 11:51 | [BE] Aggiungere LocationID al modello | 50268 | Closed |  |  |  | Main\Products\POS Partners\POS |  | 2
50276 | Task | Main |  | 2024-02-15 09:35 | 2024-07-10 11:51 | 2024-07-10 11:51 | [BE] Aggiornare la rotta | 50268 | Closed |  |  |  | Main\Products\POS Partners\POS |  | 2
53959 | Task | Main |  | 2024-03-22 10:45 | 2024-06-13 18:01 | 2024-06-13 18:01 | [FE] Aggiornare modello CenterData | 50268 | Closed |  |  |  | Main\Products\Square\POS\Integration |  | 2
53960 | Task | Main |  | 2024-03-22 10:45 | 2024-06-13 17:48 | 2024-06-13 17:48 | [FE] Refactor chiamata center-list | 50268 | Closed |  |  |  | Main\Products\Square\POS\Integration |  | 2
53961 | Task | Main |  | 2024-03-22 10:46 | 2024-06-13 17:48 | 2024-06-13 17:48 | [FE] Rimuovere controllo get-by-id per ogni centro | 50268 | Closed |  |  |  | Main\Products\Square\POS\Integration |  | 2
63104 | Task | Main\2024-Q2\117 |  | 2024-06-12 16:47 | 2024-06-13 17:40 | 2024-06-13 17:40 | [FE] Creare una ensure function per il check del token | 50268 | Closed |  |  |  | Main\Products\Square\POS\Integration |  | 2
50571 | Tech Story | Main\2024-Q1\109 | Backend | 2024-02-19 14:26 | 2025-01-20 10:49 | 2024-02-28 14:58 | Resolve todo from pr 4310 | 50759 | Closed |  |  |  | Main\Products\Square\POS\Integration
53429 | User Story | Main | Backend; Cloud; to-refine | 2024-03-18 10:55 | 2025-11-05 14:33 |  | Delete token if square response is unauthorized | 50759 | ToDo |  |  | Same as parent | Main\Products\Square\POS\Integration |  | 2
48931 | User Story | Main | Backend; Backend POS; Frontend | 2024-01-29 15:27 | 2025-11-05 14:33 |  | Delete old PAT Pairing on Square Flow | 50759 | ToDo |  |  | Same as parent | Main\Products\Square\POS\Integration |  | 2
49358 | User Story | Main | Backend | 2024-02-05 12:46 | 2025-11-05 14:33 |  | Remove duplicate method | 50759 | New |  |  | Same as parent | Main\Products\Square\POS\Integration |  | 2
49671 | Tech Story | Main\2024-Q1\110 | Backend; Cloud | 2024-02-08 14:18 | 2024-05-27 17:24 | 2024-03-08 17:22 | Square API Version | 50759 | Closed |  |  |  | Main\Products\Square\POS\Integration
71690 | User Story | Main |  | 2024-10-17 17:50 | 2025-09-10 16:46 |  | Table SquareCompanyOAuth unique on MerchantId | 50759 | New |  |  | Same as parent | Main\Products\Square\POS\Integration |  | 3
75978 | User Story | Main | Backend; Cloud; Conqueror; CRITICAL; QA; to-refine | 2024-12-05 12:12 | 2025-11-05 14:33 |  | [Tech Debt] Kiosk - Split CreateAndPayOrderAsync | 50759 | ToDo |  |  | Same as parent | Main\Products\Square\POS\Integration |  | 2
79970 | User Story | Main\2025-Q1\134 |  | 2025-02-03 12:20 | 2025-12-19 15:07 | 2025-02-10 16:06 | Deactivate and remove old PAT Webhooks | 50759 | Closed |  |  | Business | Main\Products\Square\POS\Integration |  | 2
95184 | User Story | Main | Backend; Cloud; Conqueror; QA | 2025-08-06 12:09 | 2025-11-05 14:33 |  | [Testing] (discovery) 5+ locations su singolo merchant su Testing Slot | 50759 | New |  |  | Same as parent | Main\Products\Square\POS\Integration |  | 1
95185 | User Story | Main | Backend; Cloud; Conqueror; QA | 2025-08-06 12:18 | 2025-11-05 14:33 |  | [Sync] setup di 5+ locations su singolo merchant su Testing Slot | 50759 | New |  |  | Same as parent | Main\Products\Square\POS\Integration |  | 1
50170 | Bug | Main\2024-Q1\110 | Cloud; QA | 2024-02-13 16:13 | 2025-01-20 10:48 | 2024-03-14 11:57 | Token is saved in wrong redis region | 50759 | Closed |  |  | Business | Main\Products\Square\POS\Integration |  | 2 | 0 – Undefined | 0 - Undefined | 0 - Undefined
64421 | Feature | Main | ktlo | 2024-06-28 14:49 | 2025-05-05 17:44 |  | [Tech debts] Release B | 76342 | New |  |  | Same as parent | Main\Teams\Backend |  | 3
64426 | User Story | Main | Backend | 2024-06-28 15:18 | 2025-07-31 08:44 |  | Create an abstract class KdsManager | 64421 | New |  |  | Business | Main\Teams\Backend |  | 2
54266 | Feature | Main | ktlo | 2024-03-27 08:54 | 2025-07-14 11:55 |  | [Tech debts] Release A | 76342 | Active |  |  | Same as parent | Main\Products\Square\POS\Integration |  | 3
56309 | User Story | Main | Backend | 2024-04-17 11:06 | 2025-11-05 14:33 |  | Make DbSquareCategorySync.DepartmentId unique | 54266 | New |  |  | Same as parent | Main\Products\Square\POS\Integration |  | 3
56618 | User Story | Main | Backend | 2024-04-19 17:25 | 2025-11-05 14:33 |  | QPortal pagina di Setup Bowling - Test GetBowlingItems route on real db | 54266 | New |  |  | Same as parent | Main\Products\Square\POS\Integration |  | 4
59193 | User Story | Main | Backend | 2024-05-06 17:09 | 2025-11-05 14:33 |  | Cache center pairing info of a company | 54266 | New |  |  | Same as parent | Main\Products\Square\POS\Integration |  | 3
61195 | User Story | Main | Backend | 2024-05-24 12:48 | 2025-11-05 14:33 |  | Rename CRUD Catalog Operations and v2 repositories | 54266 | ToDo |  |  | Same as parent | Main\Products\Square\POS\Integration |  | 4
64023 | User Story | Main | Backend; Cloud; QA | 2024-06-24 14:28 | 2025-11-05 14:33 |  | Manage LastUpdate for variations/items mapping | 54266 | ToDo |  |  | Same as parent | Main\Products\Square\POS\Integration |  | 4
64427 | User Story | Main | Backend | 2024-06-28 15:19 | 2025-11-05 14:33 |  | Do not consider empty square catalog objects | 54266 | New |  |  | Same as parent | Main\Products\Square\POS\Integration |  | 2
64654 | User Story | Main | Backend | 2024-07-03 16:09 | 2025-11-05 14:33 |  | Removed unused code (parte due la vendetta) | 54266 | ToDo |  |  | Same as parent | Main\Products\Square\POS\Integration |  | 2
54626 | Tech Story | Main\2024-Q3\118 | Backend; Cloud | 2024-04-02 09:04 | 2025-12-19 15:09 | 2024-07-02 16:09 | Remove unused old routes | 54266 | Closed |  |  |  | Main\Products\Square\POS\Integration
54267 | User Story | Main | Backend; Cloud | 2024-03-27 08:56 | 2025-11-05 14:33 |  | Manage FirstImportStatus updates with signalR | 54266 | ToDo |  |  | Same as parent | Main\Products\Square\POS\Integration |  | 4
61084 | User Story | Main | Backend | 2024-05-23 11:48 | 2025-11-05 14:33 |  | Cloud only manage Deleted and not IsExpired for modifiers | 54266 | New |  |  | Same as parent | Main\Products\Square\POS\Integration |  | 3
91538 | User Story | Main\2025-Q3\145 | Analysis; Backend; Cloud; Conqueror; No QA Needed; No Test Needed; Not ready to test yet | 2025-06-23 17:23 | 2025-07-23 01:13 | 2025-07-17 09:14 | [Sync] Discovery individuazione automatica degli errori | 54266 | Closed |  |  | Business | Main\Products\Square\POS\Integration |  | 2
91224 | User Story | Main\2025-Q3\145 | Analysis; Backend; Cloud; Conqueror | 2025-06-20 16:46 | 2025-07-18 10:09 | 2025-07-18 10:09 | [Sync] Discovery gestione Categorie omonimi su Square | 54266 | Closed |  |  | Business | Main\Products\Square\POS\Integration |  | 2
91261 | User Story | Main\2025-Q3\146 | Cloud; Conqueror | 2025-06-20 18:01 | 2025-08-01 06:45 | 2025-08-01 06:45 | [Sync] documento di overview sul funzionamento della sync | 54266 | Closed |  |  | Business | Main\Products\Square\POS\Integration |  | 2
75823 | Feature | Main | ktlo | 2024-12-03 15:40 | 2025-01-31 16:14 |  | C1 - E2E Testing Coverage | 76342 | Active |  |  | Same as parent | Main\Products\Square\POS\Integration |  | 3
75824 | User Story | Main\2024-Q4\130 | Backend; Cloud; tech debt | 2024-12-03 15:43 | 2025-01-16 18:00 | 2024-12-12 09:47 | Test: Create and pay a reservation order (no deposit) | 75823 | Closed |  |  | Business | Main\Products\Square\POS\Integration |  | 2
75825 | User Story | Main\2024-Q4\130 | Backend; Cloud; tech debt | 2024-12-03 15:45 | 2025-01-16 18:00 | 2024-12-18 14:52 | Test: Create and pay a reservation order (with deposit) | 75823 | Closed |  |  | Business | Main\Products\Square\POS\Integration |  | 2
75826 | User Story | Main | Backend; Cloud; tech debt | 2024-12-03 15:46 | 2025-11-05 14:33 |  | Test: add a deposit to a reservation | 75823 | New |  |  | Same as parent | Main\Products\Square\POS\Integration |  | 2
75827 | User Story | Main | Backend; Cloud; tech debt | 2024-12-03 15:49 | 2025-11-05 14:33 |  | Test: edit a deposit in a reservation | 75823 | New |  |  | Same as parent | Main\Products\Square\POS\Integration |  | 2
75828 | User Story | Main | Backend; Cloud; tech debt | 2024-12-03 15:50 | 2025-11-05 14:33 |  | Test: delete and modify a payment | 75823 | New |  |  | Same as parent | Main\Products\Square\POS\Integration |  | 2
75829 | User Story | Main | Backend; Cloud; tech debt | 2024-12-03 15:51 | 2025-11-05 14:33 |  | Test: calcolo di un ordine di deposito su una reservation | 75823 | New |  |  | Same as parent | Main\Products\Square\POS\Integration |  | 2
75830 | User Story | Main | Backend; Cloud; tech debt | 2024-12-03 15:53 | 2025-11-05 14:33 |  | Test: restore a tab | 75823 | New |  |  | Same as parent | Main\Products\Square\POS\Integration |  | 2
75831 | User Story | Main\2024-Q4\130 | Backend; Cloud; tech debt | 2024-12-03 15:55 | 2025-01-16 18:00 | 2024-12-18 09:31 | Test: F&B order create and pay | 75823 | Closed |  |  | Business | Main\Products\Square\POS\Integration |  | 2
75832 | User Story | Main\2025-Q1\133 | Backend; Cloud; tech debt | 2024-12-03 15:59 | 2025-01-31 14:42 | 2025-01-31 14:42 | Test: Lane order create and pay | 75823 | Closed |  |  | Business | Main\Products\Square\POS\Integration |  | 2
75833 | User Story | Main | Backend; Cloud; tech debt | 2024-12-03 16:00 | 2025-11-05 14:33 |  | Test: Split order create, pay and complete | 75823 | New |  |  | Same as parent | Main\Products\Square\POS\Integration |  | 2
75834 | User Story | Main | Backend; Cloud; tech debt | 2024-12-03 16:05 | 2025-11-05 14:33 |  | Test: Create and pay order -> timeout -> try again -> complete | 75823 | New |  |  | Same as parent | Main\Products\Square\POS\Integration |  | 2
75835 | User Story | Main | Backend; Cloud; tech debt | 2024-12-03 16:08 | 2025-11-05 14:33 |  | Test: add deposit to a reservation -> no show | 75823 | New |  |  | Same as parent | Main\Products\Square\POS\Integration |  | 2
75836 | User Story | Main | Backend; Cloud; tech debt | 2024-12-03 16:09 | 2025-11-05 14:33 |  | Test: add deposit to a reservation -> delete reservation | 75823 | New |  |  | Same as parent | Main\Products\Square\POS\Integration |  | 2
75838 | User Story | Main | Backend; Cloud; tech debt | 2024-12-03 16:16 | 2025-11-05 14:33 |  | Test: calcolo di un ordine di refund | 75823 | New |  |  | Same as parent | Main\Products\Square\POS\Integration |  | 2
75839 | User Story | Main | Backend; Cloud; tech debt | 2024-12-03 16:18 | 2025-11-05 14:33 |  | Test: print recepit after order completion | 75823 | New |  |  | Same as parent | Main\Products\Square\POS\Integration |  | 2
75840 | User Story | Main | Backend; Cloud; tech debt | 2024-12-03 16:23 | 2025-11-05 14:33 |  | Test: edit a deposit in a reservation and then pay it | 75823 | New |  |  | Same as parent | Main\Products\Square\POS\Integration |  | 2
75995 | User Story | Main\2024-Q4\130 | Backend; Cloud; tech debt | 2024-12-05 15:25 | 2025-01-16 18:00 | 2024-12-18 14:52 | Test: Pay a reservation order (with collected deposit ) | 75823 | Closed |  |  | Business | Main\Products\Square\POS\Integration |  | 2
77574 | User Story | Main\2025-Q1\133 | Backend; Tech DIscovery | 2025-01-07 17:22 | 2025-01-31 16:31 | 2025-01-31 16:31 | [Tech Discovery] Individuare Unit Test | 75823 | Closed |  |  | Business | Main\Products\Square\POS\Integration |  | 2
76343 | Feature | Main | ktlo | 2024-12-09 17:04 | 2025-01-23 17:37 |  | Comprehensive Mapping of Technical Debt | 76342 | Active |  |  | Same as parent | Main\Products\Square\POS\Integration |  | 3
30166 | User Story | Main | Backend; Team POS | 2023-02-20 11:23 | 2025-03-14 17:18 | 2025-03-14 17:18 | Creare la documentazione per la sandbox di Square | 76343 | Closed |  |  | Business | Main\Products\Square\POS\Integration |  | 2
32365 | User Story | Main | Backend | 2023-03-30 11:55 | 2025-11-05 14:33 |  | Sostituire su CenterEconomical la chiamata rest della complete payment | 76343 | ToDo |  |  | Same as parent | Main\Products\Square\POS\Integration |  | 2
39337 | Tech Story | Main\2023-Q3\96 | Backend; Frontend | 2023-08-07 14:59 | 2025-02-15 13:11 | 2023-08-31 14:15 | Handle 429 Too many request | 76343 | Closed |  |  |  | Main\Products\POS Partners\POS
40286 | Task | Main\2023-Q3\96 |  | 2023-08-31 12:30 | 2023-08-31 14:14 | 2023-08-31 14:14 | [FE]- Modifica dei parametri in ingresso della GetLocations (Aggiunta di CenterId) | 39337 | Closed |  |  |  | Main\Products\POS Partners\POS |  | 2
39477 | User Story | Main | Backend; Team POS | 2023-08-09 09:28 | 2025-11-05 14:33 |  | Gestire la Currency di Square nei modificatori | 76343 | ToDo |  |  | Same as parent | Main\Products\Square\POS\Integration |  | 2
45074 | User Story | Main | Backend; Team POS | 2023-11-09 16:38 | 2025-03-14 17:31 | 2025-03-14 17:31 | Create a storage to collect events before sending them to a REST API / Queue | 76343 | Closed |  |  | Business | Main\Teams\Backend |  | 2
52194 | User Story | Main | Backend | 2024-03-04 17:49 | 2025-07-31 08:44 |  | Qamf.Eft.Payments square version | 76343 | New |  |  | Business | Main\Teams\Backend |  | 2
52195 | User Story | Main\2025-Q1\135 | Backend; CRITICAL; Payments; QA | 2024-03-04 17:52 | 2025-03-20 17:55 | 2025-02-28 10:09 | Update square nuget version | 76343 | Closed |  |  | Business | Main\Products\Square\POS\Integration |  | 2
81505 | Task | Main\2025-Q1\135 |  | 2025-02-19 16:38 | 2025-02-19 17:53 | 2025-02-19 17:53 | QCloudApp | 52195 | Closed |  |  |  | Main\Products\Square\POS\Integration |  | 2
81506 | Task | Main\2025-Q1\135 |  | 2025-02-19 16:38 | 2025-02-19 17:53 | 2025-02-19 17:53 | Qamf.Eft.Payments | 52195 | Closed |  |  |  | Main\Products\Square\POS\Integration |  | 2
81535 | Task | Main\2025-Q1\135 |  | 2025-02-19 17:53 | 2025-02-19 18:01 | 2025-02-19 18:01 | Aggiornare Conqueror | 52195 | Closed |  |  |  | Main\Products\Square\POS\Integration |  | 2
81536 | Task | Main\2025-Q1\135 |  | 2025-02-19 17:54 | 2025-02-28 15:09 | 2025-02-28 15:09 | Chiudere Qamf.Eft.Payments su QCloudApp e Conqueror | 52195 | Closed |  |  |  | Main\Products\Square\POS\Integration |  | 2
46148 | User Story | Main | Backend; Team POS | 2023-11-30 12:40 | 2025-03-14 17:33 | 2025-03-14 17:33 | Ridisegnare la gestione di webhook esterne | 76343 | Closed |  |  | Business | Main\Teams\Backend |  | 3
64657 | User Story | Main\2025-Q2\141 | Backend; Cloud; tech debt | 2024-07-03 16:27 | 2025-07-09 11:37 | 2025-05-20 15:28 | Dismiss old webhook management | 76343 | Closed |  |  | Business | Main\Products\Square\POS\Integration |  | 3
65221 | User Story | Main | Backend | 2024-07-10 11:40 | 2025-11-05 14:33 |  | Remove old routes of center pairings | 76343 | ToDo |  |  | Same as parent | Main\Products\Square\POS\Integration |  | 3
65222 | User Story | Main\2025-Q2\141 | Backend | 2024-07-10 11:42 | 2025-10-06 13:27 | 2025-05-23 17:31 | Remove old CenterToSquare controller | 76343 | Closed |  |  | Business | Main\Products\Square\POS\Integration |  | 3
66584 | Tech Story | Main | Backend | 2024-08-02 14:21 | 2025-09-10 16:46 |  | Add events for web and kiosk receipts | 76343 | New |  |  |  | Main\Products\Square\POS\Integration
66941 | Tech Story | Main\2024-Q3\123 | Backend | 2024-08-08 16:15 | 2025-01-23 14:47 | 2024-09-04 08:54 | Manage other currency than USD | 76343 | Closed |  |  |  | Main\Teams\POS
70639 | User Story | Main\2025-Q1\134 | Backend; Cloud; QA; to-refine | 2024-10-04 10:19 | 2025-03-20 17:55 | 2025-02-12 15:58 | OrderManager refactory and cleanup | 76343 | Closed |  |  | Business | Main\Products\Square\POS\Integration |  | 2
80683 | Issue | Main\2025-Q1\134 |  | 2025-02-11 15:02 | 2025-02-12 15:56 | 2025-02-12 15:56 | Pagamento di un conto preautorizzato - error | 70639 | Closed |  |  |  | Main\Products\Square\POS\Integration |  | 2
72711 | User Story | Main\2025-Q1\133 | QA | 2024-10-28 14:38 | 2025-01-31 14:54 | 2025-01-31 14:54 | [Cloud] Integrazione NRT POS 1/2 | 76343 | Closed |  |  | Business | Main\Products\Square\POS\Integration |  | 2
72712 | User Story | Main\2025-Q1\134 | QA | 2024-10-28 14:39 | 2025-02-10 09:49 | 2025-02-10 09:49 | [Conqueror] Integrazione NRT ExternalPosMode | 76343 | Closed |  |  | Business | Main\Products\Square\POS\Integration |  | 2
76326 | User Story | Main\2025-Q1\135 | Backend; Cloud; Conqueror; QA; tech debt | 2024-12-09 15:52 | 2026-02-11 13:05 | 2025-02-24 11:59 | [Leagues] Separate Controllers and manager models to better separate the flows | 76343 | Closed |  |  | Business | Main\Products\Square\POS\Integration |  | 1
81702 | Bug | Main\2025-Q1\135 | Cloud; Conqueror; Develop Only; QA | 2025-02-21 17:08 | 2025-03-20 17:55 | 2025-02-28 19:20 | League - pay out error | 76326 | Closed |  |  | Business | Main\Products\Square\POS\Integration |  | 2 | 0 – Undefined | 0 - Undefined | 0 - Undefined
76400 | User Story | Main | Backend; Cloud; Conqueror; Design; Discovery; QA; tech debt | 2024-12-10 11:24 | 2026-02-11 13:05 |  | [Leagues] Tech Discovery - Manage misalignment in CQ when voiding a league | 76343 | ToDo |  |  | Same as parent | Main\Products\Square\POS\Integration |  | 2
76598 | User Story | Main | Backend; Cloud; QA; tech debt | 2024-12-13 00:29 | 2025-11-05 14:33 |  | Review and uniform SQO Cloud Errors | 76343 | ToDo |  |  | Same as parent | Main\Products\Square\POS\Integration |  | 1
76785 | User Story | Main | Backend; Cloud; Conqueror; Tech DIscovery; to-refine | 2024-12-17 00:15 | 2025-11-05 14:33 |  | [Tech Discovery] Automatic fix for broken reservations | 76343 | ToDo |  |  | Same as parent | Main\Products\Square\POS\Integration |  | 2
76848 | User Story | Main | Backend; Cloud; tech debt | 2024-12-17 13:48 | 2025-11-05 14:33 |  | Remove CMP Exp Features from Envs and src | 76343 | ToDo |  |  | Same as parent | Main\Products\Square\POS\Integration |  | 3
76849 | User Story | Main\2025-Q1\136 | Backend; Cloud; tech debt | 2024-12-17 13:50 | 2025-03-14 17:16 | 2025-03-05 08:58 | Turn-on disabled E2E Tests and stabilize current tests | 76343 | Closed |  |  | Business | Main\Products\Square\POS\Integration |  | 2
76897 | User Story | Main\2025-Q1\134 | Backend; Cloud; Conqueror; QA; tech debt | 2024-12-17 17:25 | 2025-02-25 14:59 | 2025-02-07 11:45 | SquareTeamMemberException from SQF350 to SQF370 | 76343 | Closed |  |  | Business | Main\Products\Square\POS\Integration |  | 1
76899 | User Story | Main | Backend; Cloud; QA; tech debt | 2024-12-17 17:27 | 2025-11-05 14:33 |  | [Kiosk - Checkin] Remove CreateAndPayOrder and split in two distinct operations in CQ | 76343 | ToDo |  |  | Same as parent | Main\Products\Square\POS\Integration |  | 2
76922 | User Story | Main | Backend; Cloud; tech debt | 2024-12-18 09:17 | 2025-11-05 14:33 |  | [Tech Discovery] Remove call to ExternalPos for getting integration status info while retrieving components | 76343 | ToDo |  |  | Same as parent | Main\Products\Square\POS\Integration |  | 2
79197 | Task | Main |  | 2025-01-26 08:12 | 2025-01-26 08:12 |  | Supporto OpEf | 76922 | ToDo |  |  |  | Main\Products\Square\POS\Integration |  | 2
76924 | User Story | Main\2025-Q1\135 | Backend; Cloud | 2024-12-18 09:42 | 2025-03-20 17:55 | 2025-02-28 13:27 | Creazione Channel su Teams per la verifica dei problemi POS | 76343 | Closed |  |  | Business | Main\Products\Square\POS\Integration |  | 1
78454 | Task | Main |  | 2025-01-17 12:15 | 2025-02-23 15:38 | 2025-02-23 15:38 | Supporto da CE per un'ora di Fustini che l'ha già implementato simile | 76924 | Closed |  |  |  | Main\Products\Square\POS\Integration |  | 2
76953 | User Story | Main | Backend; Cloud; QA; tech debt | 2024-12-18 14:06 | 2025-11-05 14:33 |  | Make all the refunds sequentials and not parallel like done for the leagues | 76343 | ToDo |  |  | Same as parent | Main\Products\Square\POS\Integration |  | 2
76962 | User Story | Main\2025-Q3\145 | Backend; Cloud | 2024-12-18 16:43 | 2025-07-23 01:13 | 2025-07-21 12:36 | Encrypt & decrypt Square JWT (db + redis) | 76343 | Closed |  |  | Business | Main\Products\Square\POS\Integration |  | 2
92171 | Task | Main\2025-Q3\145 |  | 2025-07-04 12:50 | 2025-07-15 09:44 | 2025-07-15 09:44 | discovery su come aggiungere il keyvault per leggere le 2 chiavi sulla QCloudApp | 76962 | Closed |  |  |  | Main\Products\Square\POS\Integration |  | 2
92172 | Task | Main\2025-Q3\145 |  | 2025-07-04 12:52 | 2025-07-15 09:45 | 2025-07-15 09:45 | uso access token su ExtPos | 76962 | Closed |  |  |  | Main\Products\Square\POS\Integration |  | 2
92173 | Task | Main\2025-Q3\145 |  | 2025-07-04 12:53 | 2025-07-15 09:46 | 2025-07-15 09:46 | refresh su securitysvc | 76962 | Closed |  |  |  | Main\Products\Square\POS\Integration |  | 2
92176 | Task | Main\2025-Q3\145 |  | 2025-07-04 12:58 | 2025-07-17 12:07 | 2025-07-17 12:07 | loop di documentazione sul processo | 76962 | Closed |  |  |  | Main\Products\Square\POS\Integration |  | 2
92177 | Task | Main\2025-Q3\145 |  | 2025-07-04 13:00 | 2025-07-16 17:01 | 2025-07-16 17:01 | cache invalidation | 76962 | Closed |  |  |  | Main\Products\Square\POS\Integration |  | 2
76963 | User Story | Main | Backend; Cloud | 2024-12-18 16:43 | 2025-11-05 14:33 |  | Api Local backend rest oriented | 76343 | New |  |  | Same as parent | Main\Products\Square\POS\Integration |  | 2
76964 | User Story | Main | Backend; Cloud | 2024-12-18 16:43 | 2025-11-05 14:33 |  | Invio notifiche sul channel Teams di anomalie in corso | 76343 | ToDo |  |  | Same as parent | Main\Products\Square\POS\Integration |  | 2
76974 | User Story | Main | Backend; Cloud | 2024-12-19 09:41 | 2025-11-05 14:33 |  | Attivare test square automatici in release | 76343 | ToDo |  |  | Same as parent | Main\Products\Square\POS\Integration |  | 2
76975 | Task | Main |  | 2024-12-19 09:49 | 2025-01-07 11:39 |  | Il fallimento blocca la creazione della release? | 76974 | ToDo |  |  |  | Main\Products\Square\POS\Integration |  | 2
77091 | User Story | Main | Backend; Cloud; Conqueror; tech debt; to refine | 2024-12-20 12:07 | 2025-11-05 14:33 |  | New API (or equivalent) to detect and fix automatically the reservations in CQ and Cloud | 76343 | New |  |  | Same as parent | Main\Products\Square\POS\Integration |  | 4
77115 | User Story | Main | Backend; Cloud; Design; tech debt; to refine | 2024-12-21 13:16 | 2025-11-05 14:33 |  | New SQO Cloud for managing the exception "NotEnoughFundsForRefundException" | 76343 | New |  |  | Same as parent | Main\Products\Square\POS\Integration |  | 1
78425 | User Story | Main | Backend; Cloud; QA; to-refine | 2025-01-17 07:50 | 2025-11-05 14:33 |  | Move TeamMembers to CompanySvc | 76343 | New |  |  | Same as parent | Main\Products\Square\POS\Integration |  | 2
78426 | Task | Main |  | 2025-01-17 07:51 | 2025-01-17 07:51 |  | Gestire l'aggiunta dei team members e la rimozione via WebHook Square in modo asincrono | 78425 | ToDo |  |  |  | Main\Products\Square\POS\Integration |  | 2
78427 | Task | Main |  | 2025-01-17 07:52 | 2025-01-17 07:53 |  | Gestire i square team members anche per location non solo per merchant | 78425 | ToDo |  |  |  | Main\Products\Square\POS\Integration |  | 2
79602 | User Story | Main |  | 2025-01-29 15:44 | 2025-11-05 14:33 |  | [Conqueror] Mettere i required nei modelli request | 76343 | New |  |  | Same as parent | Main\Teams\POS |  | 2
79672 | User Story | Main\2025-Q1\134 | Backend; Cloud; No Critical | 2025-01-30 13:27 | 2025-03-25 11:18 | 2025-02-07 17:32 | Remove ObjectDispose exception of ServiceBus for CenterExternalPos | 76343 | Closed |  |  | Business | Main\Products\Square\POS\Integration |  | 2
79836 | User Story | Main\2025-Q1\137 | Backend; Cloud | 2025-01-31 16:36 | 2025-03-18 18:22 | 2025-03-18 10:13 | Removed KDS Dummies | 76343 | Closed |  |  | Business | Main\Products\Square\POS\Integration |  | 2
80006 | User Story | Main |  | 2025-02-03 14:23 | 2025-11-05 14:33 |  | Switchare i centri con la exp feature a CMP POS | 76343 | ToDo |  |  | Same as parent | Main\Products\Square\POS\Integration |  | 2
79032 | User Story | Main | Backend; Cloud; Design; Discovery | 2025-01-23 15:47 | 2025-11-05 14:33 |  | Visualizzazione su ADE di log su eventi e anomalie | 76343 | New |  |  | Same as parent | Main\Products\Square\POS\Integration |  | 2
78180 | User Story | Main | Backend; Cloud; to-refine | 2025-01-15 01:33 | 2025-11-05 14:33 |  | [Discovery] come migliorare il flusso che definisce se l'integrazione è attiva | 76343 | New |  |  | Same as parent | Main\Products\Square\POS\Integration |  | 2
85382 | User Story | Main | Backend; Cloud | 2025-04-07 14:17 | 2025-11-05 14:33 |  | Refactor Square providers | 76343 | New |  |  | Same as parent | Main\Products\Square\POS\Integration |  | 2
81020 | User Story | Main\2025-Q1\137 | Backend; Cloud | 2025-02-15 13:11 | 2025-03-18 18:22 | 2025-03-17 14:20 | Remove /environment-token-exists route | 76343 | Closed |  |  | Business | Main\Products\Square\POS\Integration |  | 2
82658 | User Story | Main |  | 2025-03-05 08:58 | 2025-11-05 14:34 |  | E2E - Activate disabled test | 76343 | New |  |  | Same as parent | Main\Products\Square\POS\Integration |  | 2
82926 | User Story | Main\2025-Q2\141 | Backend; Cloud; QA | 2025-03-07 14:58 | 2025-07-09 11:37 | 2025-05-19 12:46 | Refactor SquareImporter class | 76343 | Closed |  |  | Business | Main\Products\Square\POS\Integration |  | 2
83168 | User Story | Main\2025-Q1\136 | Backend; Conqueror; QA | 2025-03-12 09:59 | 2025-04-07 16:07 | 2025-03-14 17:56 | Spostare Square settings nelle Globals | 76343 | Closed |  |  | Business | Main\Products\Square\POS\Integration |  | 2
94768 | User Story | Main | Backend; Cloud; Conqueror | 2025-08-01 12:36 | 2025-11-05 14:34 |  | [Tech Discovery] introduction of redeem transactions refunds | 76343 | ToDo |  |  | Same as parent | Main\Products\Square\POS\Integration |  | 2
95686 | User Story | Main | Backend; Cloud; Conqueror; QA | 2025-08-13 16:01 | 2025-11-05 14:34 |  | remove usage of deprecated payments events (part 1 of 2) | 76343 | New |  |  | Same as parent | Main\Products\Square\POS\Integration |  | 2
99850 | Tech Story | Main | Backend; Cloud; QA; QA Estimation Needed | 2025-10-10 12:30 | 2026-02-16 11:01 |  | UNDO_SUCCEEDED event dismission and alignment on UNDO_PENDING | 76343 | New |  |  |  | Main\Products\Square\POS\Integration
100075 | User Story | Main | Backend; Cloud; Conqueror | 2025-10-13 10:18 | 2026-02-16 11:01 |  | [Discovery] improvement plan for sync again | 76343 | ToDo |  |  | Same as parent | Main\Products\Square\POS\Integration |  | 2
100991 | User Story | Main | Backend; Cloud; Conqueror | 2025-10-24 18:32 | 2026-02-03 12:17 |  | [Observability] review ed improvement degli eventi delle leagues | 76343 | ToDo |  |  | Same as parent | Main\Products\Square\POS\Integration |  | 2
106012 | User Story | Main\2026-Q1\161 | Backend; Sync Square | 2026-01-09 12:14 | 2026-02-09 10:14 |  | prevent sync failures during a cloud release freeze | 76343 | On wait |  |  | Same as parent | Main\Products\Square\POS\Integration |  | 2
106050 | Tech Story | Main | Backend | 2026-01-09 17:25 | 2026-02-16 11:01 |  | [Discovery] remove redis polling during kiosk sync call | 76343 | New |  |  |  | Main\Products\Square\POS\Integration
76930 | Bug | Main\2025-Q1\135 | Backend; Cloud; QA; to-refine | 2024-12-18 10:21 | 2025-03-20 17:55 | 2025-02-28 19:20 | Mitigate problem 429 rate limit - TooManyRequests | 76343 | Closed |  |  | Business | Main\Products\Square\POS\Integration |  | 2 | 0 – Undefined | 0 - Undefined | 0 - Undefined
82247 | Bug | Main\2025-Q1\135 | Backend; Cloud; QA; to-refine | 2025-03-02 06:54 | 2025-03-20 17:55 | 2025-03-03 10:53 | Mitigate problem 429 rate limit - TooManyRequests | 76343 | Closed |  |  | Business | Main\Products\Square\POS\Integration |  | 2 | 0 – Undefined | 0 - Undefined | 0 - Undefined
78463 | Feature | Main | ktlo | 2025-01-17 12:33 | 2025-07-14 11:55 |  | GraphQL | 76342 | New |  |  | Same as parent | Main\Products\Square\POS\Integration |  | 3
78464 | User Story | Main\2025-Q1\133 |  | 2025-01-17 12:34 | 2025-01-27 09:32 | 2025-01-27 09:31 | Creare un nuovo microservizio nel localbackend per GraphQL | 78463 | Closed |  |  | Business | Main\Products\Square\POS\Integration |  | 2
79807 | Feature | Main |  | 2025-01-31 16:15 | 2025-07-14 11:55 |  | Unit Testing Coverage | 76342 | New |  |  | Same as parent | Main\Products\Square\POS\Integration |  | 3
79809 | User Story | Main\2025-Q1\134 | Backend; Cloud; QA | 2025-01-31 16:16 | 2025-03-20 17:55 | 2025-02-12 15:58 | OrdersManager - Coverage > 70% | 79807 | Closed |  |  | Business | Main\Products\Square\POS\Integration |  | 2
79810 | User Story | Main | Backend; Cloud | 2025-01-31 16:17 | 2025-11-05 14:33 |  | LeagueOrdersManager - Coverage > 70% | 79807 | New |  |  | Same as parent | Main\Products\Square\POS\Integration |  | 2
79811 | User Story | Main | Backend; Cloud | 2025-01-31 16:17 | 2025-11-05 14:33 |  | LeagueDepositManager - Coverage > 70% | 79807 | New |  |  | Same as parent | Main\Products\Square\POS\Integration |  | 2
79812 | [7 empty] | undefined
79814 | [7 empty] | undefined
79815 | [7 empty] | undefined
79817 | [7 empty] | undefined
79818 | [7 empty] | undefined
79820 | [7 empty] | undefined
79821 | [7 empty] | undefined
79823 | [7 empty] | undefined
79824 | [7 empty] | undefined
79825 | [7 empty] | undefined
79826 | [7 empty] | undefined
79827 | [7 empty] | undefined
79828 | [7 empty] | undefined
79829 | [7 empty] | undefined
79830 | [7 empty] | undefined
94701 | [7 empty] | undefined
93671 | [7 empty] | undefined
94702 | [7 empty] | undefined
94720 | [7 empty] | undefined
94721 | [7 empty] | undefined
94762 | [7 empty] | undefined
94766 | [7 empty] | undefined
94182 | [7 empty] | undefined
79450 | [7 empty] | undefined
72622 | [7 empty] | undefined
64575 | [7 empty] | undefined
65013 | [7 empty] | undefined
69668 | [7 empty] | undefined
70624 | [7 empty] | undefined
70628 | [7 empty] | undefined
72630 | [7 empty] | undefined
75239 | [7 empty] | undefined
75246 | [7 empty] | undefined
75248 | [7 empty] | undefined
82237 | [7 empty] | undefined
82764 | [7 empty] | undefined
82896 | [7 empty] | undefined
79451 | [7 empty] | undefined
80852 | [7 empty] | undefined
80853 | [7 empty] | undefined
80867 | [7 empty] | undefined
80874 | [7 empty] | undefined
80876 | [7 empty] | undefined
81456 | [7 empty] | undefined
81748 | [7 empty] | undefined
81749 | [7 empty] | undefined
82235 | [7 empty] | undefined
79466 | [7 empty] | undefined
81199 | [7 empty] | undefined
81419 | [7 empty] | undefined
84578 | [7 empty] | undefined
85039 | [7 empty] | undefined
86131 | [7 empty] | undefined
86130 | [7 empty] | undefined
81426 | [7 empty] | undefined
82004 | [7 empty] | undefined
82005 | [7 empty] | undefined
82812 | [7 empty] | undefined
82816 | [7 empty] | undefined
82817 | [7 empty] | undefined
82851 | [7 empty] | undefined
83379 | [7 empty] | undefined
79458 | [7 empty] | undefined
89149 | [7 empty] | undefined
93695 | [7 empty] | undefined
95693 | [7 empty] | undefined
95924 | [7 empty] | undefined
95925 | [7 empty] | undefined
95926 | [7 empty] | undefined
93702 | [7 empty] | undefined
96085 | [7 empty] | undefined
97757 | [7 empty] | undefined
97758 | [7 empty] | undefined
97767 | [7 empty] | undefined
98128 | [7 empty] | undefined
93722 | [7 empty] | undefined
96008 | [7 empty] | undefined
96009 | [7 empty] | undefined
96010 | [7 empty] | undefined
93733 | [7 empty] | undefined
96086 | [7 empty] | undefined
98478 | [7 empty] | undefined
98491 | [7 empty] | undefined
98513 | [7 empty] | undefined
98416 | [7 empty] | undefined
93736 | [7 empty] | undefined
98433 | [7 empty] | undefined
98131 | [7 empty] | undefined
98132 | [7 empty] | undefined
98288 | [7 empty] | undefined
93737 | [7 empty] | undefined
98432 | [7 empty] | undefined
98145 | [7 empty] | undefined
98146 | [7 empty] | undefined
98225 | [7 empty] | undefined
93738 | [7 empty] | undefined
93739 | [7 empty] | undefined
93743 | [7 empty] | undefined
98667 | [7 empty] | undefined
98759 | [7 empty] | undefined
98875 | [7 empty] | undefined
98226 | [7 empty] | undefined
99247 | [7 empty] | undefined
93744 | [7 empty] | undefined
98963 | [7 empty] | undefined
98964 | [7 empty] | undefined
98969 | [7 empty] | undefined
98970 | [7 empty] | undefined
99919 | [7 empty] | undefined
99923 | [7 empty] | undefined
99420 | [7 empty] | undefined
93974 | [7 empty] | undefined
97006 | [7 empty] | undefined
97367 | [7 empty] | undefined
98069 | [7 empty] | undefined
94087 | [7 empty] | undefined
94088 | [7 empty] | undefined
94089 | [7 empty] | undefined
101305 | [7 empty] | undefined
94326 | [7 empty] | undefined
98957 | [7 empty] | undefined
98961 | [7 empty] | undefined
98971 | [7 empty] | undefined
99099 | [7 empty] | undefined
99100 | [7 empty] | undefined
99174 | [7 empty] | undefined
98165 | [7 empty] | undefined
94264 | [7 empty] | undefined
95664 | [7 empty] | undefined
96381 | [7 empty] | undefined
97237 | [7 empty] | undefined
97239 | [7 empty] | undefined
97240 | [7 empty] | undefined
97500 | [7 empty] | undefined
97501 | [7 empty] | undefined
97503 | [7 empty] | undefined
97504 | [7 empty] | undefined
97505 | [7 empty] | undefined
97612 | [7 empty] | undefined
95242 | [7 empty] | undefined
96036 | [7 empty] | undefined
96037 | [7 empty] | undefined
96228 | [7 empty] | undefined
98393 | [7 empty] | undefined
96307 | [7 empty] | undefined
97241 | [7 empty] | undefined
97507 | [7 empty] | undefined
97574 | [7 empty] | undefined
97576 | [7 empty] | undefined
97577 | [7 empty] | undefined
97608 | [7 empty] | undefined
98118 | [7 empty] | undefined
96466 | [7 empty] | undefined
97243 | [7 empty] | undefined
97363 | [7 empty] | undefined
97365 | [7 empty] | undefined
97414 | [7 empty] | undefined
96473 | [7 empty] | undefined
97242 | [7 empty] | undefined
97372 | [7 empty] | undefined
97373 | [7 empty] | undefined
97488 | [7 empty] | undefined
97597 | [7 empty] | undefined
98962 | [7 empty] | undefined
98972 | [7 empty] | undefined
99740 | [7 empty] | undefined
99811 | [7 empty] | undefined
98480 | [7 empty] | undefined
98518 | [7 empty] | undefined
98666 | [7 empty] | undefined
98717 | [7 empty] | undefined
98718 | [7 empty] | undefined
98720 | [7 empty] | undefined
100530 | [7 empty] | undefined
99788 | [7 empty] | undefined
99789 | [7 empty] | undefined
99790 | [7 empty] | undefined
99791 | [7 empty] | undefined
99794 | [7 empty] | undefined
99867 | [7 empty] | undefined
101654 | [7 empty] | undefined
101684 | [7 empty] | undefined
100042 | [7 empty] | undefined
100083 | [7 empty] | undefined
100162 | [7 empty] | undefined
97822 | [7 empty] | undefined
97867 | [7 empty] | undefined
98966 | [7 empty] | undefined
98967 | [7 empty] | undefined
98973 | [7 empty] | undefined
99481 | [7 empty] | undefined
98135 | [7 empty] | undefined
98745 | [7 empty] | undefined
98965 | [7 empty] | undefined
99734 | [7 empty] | undefined
98311 | [7 empty] | undefined
98974 | [7 empty] | undefined
99515 | [7 empty] | undefined
99641 | [7 empty] | undefined
98388 | [7 empty] | undefined
98987 | [7 empty] | undefined
98392 | [7 empty] | undefined
98988 | [7 empty] | undefined
98426 | [7 empty] | undefined
99298 | [7 empty] | undefined
101558 | [7 empty] | undefined
101559 | [7 empty] | undefined
97756 | [7 empty] | undefined
93222 | [7 empty] | undefined
93906 | [7 empty] | undefined
93907 | [7 empty] | undefined
101387 | [7 empty] | undefined
93912 | [7 empty] | undefined
99251 | [7 empty] | undefined
97083 | [7 empty] | undefined
97220 | [7 empty] | undefined
99263 | [7 empty] | undefined
93223 | [7 empty] | undefined
93916 | [7 empty] | undefined
101568 | [7 empty] | undefined
93919 | [7 empty] | undefined
101518 | [7 empty] | undefined
101644 | [7 empty] | undefined
97085 | [7 empty] | undefined
97087 | [7 empty] | undefined
93248 | [7 empty] | undefined
93257 | [7 empty] | undefined
93895 | [7 empty] | undefined
93896 | [7 empty] | undefined
92359 | [7 empty] | undefined
94683 | [7 empty] | undefined
94921 | [7 empty] | undefined
96490 | [7 empty] | undefined
96554 | [7 empty] | undefined
96555 | [7 empty] | undefined
96575 | [7 empty] | undefined
98536 | [7 empty] | undefined
98537 | [7 empty] | undefined
98538 | [7 empty] | undefined
98539 | [7 empty] | undefined
98540 | [7 empty] | undefined
98541 | [7 empty] | undefined
96601 | [7 empty] | undefined
96697 | [7 empty] | undefined
98644 | [7 empty] | undefined
98645 | [7 empty] | undefined
98646 | [7 empty] | undefined
98647 | [7 empty] | undefined
98648 | [7 empty] | undefined
97588 | [7 empty] | undefined
100422 | [7 empty] | undefined
100480 | [7 empty] | undefined
93678 | [7 empty] | undefined
93680 | [7 empty] | undefined
93687 | [7 empty] | undefined
95929 | [7 empty] | undefined
93911 | [7 empty] | undefined
93905 | [7 empty] | undefined
98127 | [7 empty] | undefined
93908 | [7 empty] | undefined
97866 | [7 empty] | undefined
101450 | [7 empty] | undefined
97868 | [7 empty] | undefined
93915 | [7 empty] | undefined
93981 | [7 empty] | undefined
93982 | [7 empty] | undefined
93983 | [7 empty] | undefined
94366 | [7 empty] | undefined
94367 | [7 empty] | undefined
94368 | [7 empty] | undefined
94369 | [7 empty] | undefined
101648 | [7 empty] | undefined
79460 | [7 empty] | undefined
79461 | [7 empty] | undefined
79464 | [7 empty] | undefined
79465 | [7 empty] | undefined
81203 | [7 empty] | undefined
80795 | [7 empty] | undefined
79467 | [7 empty] | undefined
79468 | [7 empty] | undefined
79469 | [7 empty] | undefined
79470 | [7 empty] | undefined
79471 | [7 empty] | undefined
79472 | [7 empty] | undefined
79473 | [7 empty] | undefined
79474 | [7 empty] | undefined
79476 | [7 empty] | undefined
79477 | [7 empty] | undefined
79478 | [7 empty] | undefined
79479 | [7 empty] | undefined
72623 | [7 empty] | undefined
72624 | [7 empty] | undefined
72625 | [7 empty] | undefined
72626 | [7 empty] | undefined
86264 | [7 empty] | undefined
79480 | [7 empty] | undefined
79482 | [7 empty] | undefined
68610 | [7 empty] | undefined
68619 | [7 empty] | undefined
68620 | [7 empty] | undefined
76176 | [7 empty] | undefined
79483 | [7 empty] | undefined
79484 | [7 empty] | undefined
79485 | [7 empty] | undefined
79486 | [7 empty] | undefined
79488 | [7 empty] | undefined
53310 | [7 empty] | undefined
52313 | [7 empty] | undefined
53311 | [7 empty] | undefined
54538 | [7 empty] | undefined
54539 | [7 empty] | undefined
54541 | [7 empty] | undefined
53432 | [7 empty] | undefined
53502 | [7 empty] | undefined
52547 | [7 empty] | undefined
52548 | [7 empty] | undefined
75517 | [7 empty] | undefined
75518 | [7 empty] | undefined
75519 | [7 empty] | undefined
79492 | [7 empty] | undefined
79493 | [7 empty] | undefined
79494 | [7 empty] | undefined
79495 | [7 empty] | undefined
53900 | [7 empty] | undefined
53304 | [7 empty] | undefined
53399 | [7 empty] | undefined
52580 | [7 empty] | undefined
64460 | [7 empty] | undefined
65406 | [7 empty] | undefined
65409 | [7 empty] | undefined
79496 | [7 empty] | undefined
79497 | [7 empty] | undefined
61150 | [7 empty] | undefined
75233 | [7 empty] | undefined
65449 | [7 empty] | undefined
67848 | [7 empty] | undefined
67905 | [7 empty] | undefined
65767 | [7 empty] | undefined
65770 | [7 empty] | undefined
66900 | [7 empty] | undefined
67847 | [7 empty] | undefined
71246 | [7 empty] | undefined
79500 | [7 empty] | undefined
79501 | [7 empty] | undefined
79503 | [7 empty] | undefined
79504 | [7 empty] | undefined
79543 | [7 empty] | undefined
79552 | [7 empty] | undefined
79305 | [7 empty] | undefined
81569 | [7 empty] | undefined
81458 | [7 empty] | undefined
79555 | [7 empty] | undefined
84933 | [7 empty] | undefined
81817 | [7 empty] | undefined
81819 | [7 empty] | undefined
82572 | [7 empty] | undefined
82573 | [7 empty] | undefined
96476 | [7 empty] | undefined
81328 | [7 empty] | undefined
83931 | [7 empty] | undefined
101355 | [7 empty] | undefined
105378 | [7 empty] | undefined
105379 | [7 empty] | undefined
101351 | [7 empty] | undefined
101352 | [7 empty] | undefined
101353 | [7 empty] | undefined
101354 | [7 empty] | undefined
105804 | [7 empty] | undefined
105879 | [7 empty] | undefined
79673 | [7 empty] | undefined
79697 | [7 empty] | undefined
87766 | [7 empty] | undefined
81923 | [7 empty] | undefined
82977 | [7 empty] | undefined
79622 | [7 empty] | undefined
90190 | [7 empty] | undefined
79709 | [7 empty] | undefined
71316 | [7 empty] | undefined
71347 | [7 empty] | undefined
71381 | [7 empty] | undefined
76377 | [7 empty] | undefined
74172 | [7 empty] | undefined
72187 | [7 empty] | undefined
71873 | [7 empty] | undefined
73096 | [7 empty] | undefined
73103 | [7 empty] | undefined
73177 | [7 empty] | undefined
77704 | [7 empty] | undefined
77745 | [7 empty] | undefined
78405 | [7 empty] | undefined
78827 | [7 empty] | undefined
79594 | [7 empty] | undefined
78045 | [7 empty] | undefined
78046 | [7 empty] | undefined
78047 | [7 empty] | undefined
78143 | [7 empty] | undefined
80278 | [7 empty] | undefined
80285 | [7 empty] | undefined
78351 | [7 empty] | undefined
84530 | [7 empty] | undefined
79096 | [7 empty] | undefined
81764 | [7 empty] | undefined
80498 | [7 empty] | undefined
80501 | [7 empty] | undefined
80506 | [7 empty] | undefined
80507 | [7 empty] | undefined
80594 | [7 empty] | undefined
80595 | [7 empty] | undefined
79312 | [7 empty] | undefined
77135 | [7 empty] | undefined
106071 | [7 empty] | undefined
73758 | [7 empty] | undefined
77211 | [7 empty] | undefined
79538 | [7 empty] | undefined
79860 | [7 empty] | undefined
79861 | [7 empty] | undefined
79199 | [7 empty] | undefined
79695 | [7 empty] | undefined
81015 | [7 empty] | undefined
81021 | [7 empty] | undefined
81022 | [7 empty] | undefined
81138 | [7 empty] | undefined
81229 | [7 empty] | undefined
81321 | [7 empty] | undefined
80502 | [7 empty] | undefined
80508 | [7 empty] | undefined
80514 | [7 empty] | undefined
80515 | [7 empty] | undefined
81911 | [7 empty] | undefined
77293 | [7 empty] | undefined
77295 | [7 empty] | undefined
77356 | [7 empty] | undefined
77357 | [7 empty] | undefined
77359 | [7 empty] | undefined
77360 | [7 empty] | undefined
77361 | [7 empty] | undefined
77861 | [7 empty] | undefined
78528 | [7 empty] | undefined
78529 | [7 empty] | undefined
78544 | [7 empty] | undefined
77942 | [7 empty] | undefined
78840 | [7 empty] | undefined
78842 | [7 empty] | undefined
80211 | [7 empty] | undefined
78224 | [7 empty] | undefined
78853 | [7 empty] | undefined
80152 | [7 empty] | undefined
82916 | [7 empty] | undefined
105351 | [7 empty] | undefined
101258 | [7 empty] | undefined
80554 | [7 empty] | undefined
80601 | [7 empty] | undefined
80605 | [7 empty] | undefined
80608 | [7 empty] | undefined
80609 | [7 empty] | undefined
80610 | [7 empty] | undefined
80611 | [7 empty] | undefined
80612 | [7 empty] | undefined
80613 | [7 empty] | undefined
80614 | [7 empty] | undefined
80615 | [7 empty] | undefined
80616 | [7 empty] | undefined
80617 | [7 empty] | undefined
80618 | [7 empty] | undefined
80620 | [7 empty] | undefined
80621 | [7 empty] | undefined
81282 | [7 empty] | undefined
80555 | [7 empty] | undefined
80564 | [7 empty] | undefined
80900 | [7 empty] | undefined
84642 | [7 empty] | undefined
87019 | [7 empty] | undefined
87294 | [7 empty] | undefined
80901 | [7 empty] | undefined
80905 | [7 empty] | undefined
80930 | [7 empty] | undefined
81158 | [7 empty] | undefined
81187 | [7 empty] | undefined
98680 | [7 empty] | undefined
98681 | [7 empty] | undefined
98682 | [7 empty] | undefined
98683 | [7 empty] | undefined
98684 | [7 empty] | undefined
81409 | [7 empty] | undefined
83463 | [7 empty] | undefined
92045 | [7 empty] | undefined
92046 | [7 empty] | undefined
98862 | [7 empty] | undefined
100021 | [7 empty] | undefined
100039 | [7 empty] | undefined
100054 | [7 empty] | undefined
100056 | [7 empty] | undefined
100072 | [7 empty] | undefined
100074 | [7 empty] | undefined
100079 | [7 empty] | undefined
100082 | [7 empty] | undefined
100092 | [7 empty] | undefined
100291 | [7 empty] | undefined
100298 | [7 empty] | undefined
100371 | [7 empty] | undefined
100425 | [7 empty] | undefined
101089 | [7 empty] | undefined
105157 | [7 empty] | undefined
89563 | [7 empty] | undefined
88253 | [7 empty] | undefined
105541 | [7 empty] | undefined
103209 | [7 empty] | undefined
106900 | [7 empty] | undefined
103569 | [7 empty] | undefined
71794 | [7 empty] | undefined
87770 | [7 empty] | undefined
94265 | [7 empty] | undefined
92541 | [7 empty] | undefined
93470 | [7 empty] | undefined
93471 | [7 empty] | undefined
93472 | [7 empty] | undefined
93473 | [7 empty] | undefined
101842 | [7 empty] | undefined
89240 | [7 empty] | undefined
94236 | [7 empty] | undefined
85959 | [7 empty] | undefined
86350 | [7 empty] | undefined
88118 | [7 empty] | undefined
88549 | [7 empty] | undefined
94860 | [7 empty] | undefined
91001 | [7 empty] | undefined
102074 | [7 empty] | undefined
102435 | [7 empty] | undefined
102815 | [7 empty] | undefined
102362 | [7 empty] | undefined
103581 | [7 empty] | undefined
103583 | [7 empty] | undefined
103604 | [7 empty] | undefined
103771 | [7 empty] | undefined
99189 | [7 empty] | undefined
99193 | [7 empty] | undefined
94162 | [7 empty] | undefined
97421 | [7 empty] | undefined
97422 | [7 empty] | undefined
98932 | [7 empty] | undefined
98934 | [7 empty] | undefined
98989 | [7 empty] | undefined
98990 | [7 empty] | undefined
79055 | [7 empty] | undefined
79056 | [7 empty] | undefined
78719 | [7 empty] | undefined
79726 | [7 empty] | undefined
81634 | [7 empty] | undefined
82242 | [7 empty] | undefined
79057 | [7 empty] | undefined
78718 | [7 empty] | undefined
79058 | [7 empty] | undefined
86940 | [7 empty] | undefined
86941 | [7 empty] | undefined
87387 | [7 empty] | undefined
89171 | [7 empty] | undefined
90269 | [7 empty] | undefined
99799 | [7 empty] | undefined
99800 | [7 empty] | undefined
100476 | [7 empty] | undefined
100479 | [7 empty] | undefined
101829 | [7 empty] | undefined
103625 | [7 empty] | undefined
110853 | [7 empty] | undefined
110854 | [7 empty] | undefined
110855 | [7 empty] | undefined
110856 | [7 empty] | undefined
110857 | [7 empty] | undefined
110858 | [7 empty] | undefined
110859 | [7 empty] | undefined
110860 | [7 empty] | undefined
106551 | [7 empty] | undefined
106552 | [7 empty] | undefined
78848 | [7 empty] | undefined
87871 | [7 empty] | undefined
70344 | [7 empty] | undefined
71009 | [7 empty] | undefined
87872 | [7 empty] | undefined
87873 | [7 empty] | undefined
89158 | [7 empty] | undefined
90643 | [7 empty] | undefined
90644 | [7 empty] | undefined
90650 | [7 empty] | undefined
90654 | [7 empty] | undefined
90659 | [7 empty] | undefined
98940 | [7 empty] | undefined
80355 | [7 empty] | undefined
58739 | [7 empty] | undefined
53120 | [7 empty] | undefined
53490 | [7 empty] | undefined
53492 | [7 empty] | undefined
52515 | [7 empty] | undefined
52740 | [7 empty] | undefined
56503 | [7 empty] | undefined
59459 | [7 empty] | undefined
59683 | [7 empty] | undefined
62123 | [7 empty] | undefined
62653 | [7 empty] | undefined
55484 | [7 empty] | undefined
55485 | [7 empty] | undefined
55486 | [7 empty] | undefined
55488 | [7 empty] | undefined
54819 | [7 empty] | undefined
53211 | [7 empty] | undefined
53287 | [7 empty] | undefined
64554 | [7 empty] | undefined
64555 | [7 empty] | undefined
64560 | [7 empty] | undefined
64659 | [7 empty] | undefined
64660 | [7 empty] | undefined
58942 | [7 empty] | undefined
63681 | [7 empty] | undefined
64740 | [7 empty] | undefined
64044 | [7 empty] | undefined
68423 | [7 empty] | undefined
69645 | [7 empty] | undefined
53926 | [7 empty] | undefined
53927 | [7 empty] | undefined
58921 | [7 empty] | undefined
58922 | [7 empty] | undefined
58923 | [7 empty] | undefined
58924 | [7 empty] | undefined
58925 | [7 empty] | undefined
58930 | [7 empty] | undefined
58932 | [7 empty] | undefined
58935 | [7 empty] | undefined
58937 | [7 empty] | undefined
58938 | [7 empty] | undefined
58939 | [7 empty] | undefined
58940 | [7 empty] | undefined
59528 | [7 empty] | undefined
59529 | [7 empty] | undefined
59530 | [7 empty] | undefined
59531 | [7 empty] | undefined
59532 | [7 empty] | undefined
59533 | [7 empty] | undefined
59534 | [7 empty] | undefined
59535 | [7 empty] | undefined
59536 | [7 empty] | undefined
59537 | [7 empty] | undefined
59538 | [7 empty] | undefined
59548 | [7 empty] | undefined
59571 | [7 empty] | undefined
60035 | [7 empty] | undefined
64565 | [7 empty] | undefined
64576 | [7 empty] | undefined
77477 | [7 empty] | undefined
77332 | [7 empty] | undefined
80343 | [7 empty] | undefined
83374 | [7 empty] | undefined
87983 | [7 empty] | undefined
87987 | [7 empty] | undefined
88168 | [7 empty] | undefined
83782 | [7 empty] | undefined
93604 | [7 empty] | undefined
93672 | [7 empty] | undefined
95187 | [7 empty] | undefined
95188 | [7 empty] | undefined
95197 | [7 empty] | undefined
95214 | [7 empty] | undefined
99598 | [7 empty] | undefined
99599 | [7 empty] | undefined
99601 | [7 empty] | undefined
100410 | [7 empty] | undefined
98939 | [7 empty] | undefined
99735 | [7 empty] | undefined
99748 | [7 empty] | undefined
97810 | [7 empty] | undefined
97416 | [7 empty] | undefined
98091 | [7 empty] | undefined
93219 | [7 empty] | undefined
95714 | [7 empty] | undefined
96251 | [7 empty] | undefined
90655 | [7 empty] | undefined
92144 | [7 empty] | undefined
95582 | [7 empty] | undefined
95654 | [7 empty] | undefined
97968 | [7 empty] | undefined
97982 | [7 empty] | undefined
98035 | [7 empty] | undefined
98090 | [7 empty] | undefined
98431 | [7 empty] | undefined
98330 | [7 empty] | undefined
89352 | [7 empty] | undefined
96674 | [7 empty] | undefined
98120 | [7 empty] | undefined
98121 | [7 empty] | undefined
95123 | [7 empty] | undefined
98366 | [7 empty] | undefined
98441 | [7 empty] | undefined
98444 | [7 empty] | undefined
98389 | [7 empty] | undefined
98395 | [7 empty] | undefined
84531 | [7 empty] | undefined
72798 | [7 empty] | undefined
64960 | [7 empty] | undefined
64970 | [7 empty] | undefined
67694 | [7 empty] | undefined
67696 | [7 empty] | undefined
68863 | [7 empty] | undefined
69019 | [7 empty] | undefined
69038 | [7 empty] | undefined
69825 | [7 empty] | undefined
70378 | [7 empty] | undefined
70976 | [7 empty] | undefined
71002 | [7 empty] | undefined
71004 | [7 empty] | undefined
71005 | [7 empty] | undefined
71255 | [7 empty] | undefined
72232 | [7 empty] | undefined
72617 | [7 empty] | undefined
72629 | [7 empty] | undefined
71391 | [7 empty] | undefined
71785 | [7 empty] | undefined
71788 | [7 empty] | undefined
73659 | [7 empty] | undefined
73720 | [7 empty] | undefined
73721 | [7 empty] | undefined
76185 | [7 empty] | undefined
74875 | [7 empty] | undefined
75455 | [7 empty] | undefined
77401 | [7 empty] | undefined
79193 | [7 empty] | undefined
80163 | [7 empty] | undefined
71787 | [7 empty] | undefined
84532 | [7 empty] | undefined
28168 | [7 empty] | undefined
31647 | [7 empty] | undefined
33804 | [7 empty] | undefined
37460 | [7 empty] | undefined
37561 | [7 empty] | undefined
41278 | [7 empty] | undefined
42684 | [7 empty] | undefined
42687 | [7 empty] | undefined
42743 | [7 empty] | undefined
42756 | [7 empty] | undefined
43253 | [7 empty] | undefined
45256 | [7 empty] | undefined
45981 | [7 empty] | undefined
47712 | [7 empty] | undefined
47734 | [7 empty] | undefined
47735 | [7 empty] | undefined
47763 | [7 empty] | undefined
48280 | [7 empty] | undefined
50585 | [7 empty] | undefined
51325 | [7 empty] | undefined
51327 | [7 empty] | undefined
51395 | [7 empty] | undefined
51419 | [7 empty] | undefined
52415 | [7 empty] | undefined
48808 | [7 empty] | undefined
49789 | [7 empty] | undefined
55962 | [7 empty] | undefined
65025 | [7 empty] | undefined
65546 | [7 empty] | undefined
65547 | [7 empty] | undefined
55420 | [7 empty] | undefined
72699 | [7 empty] | undefined
72700 | [7 empty] | undefined
74410 | [7 empty] | undefined
75156 | [7 empty] | undefined
79724 | [7 empty] | undefined
79867 | [7 empty] | undefined
82536 | [7 empty] | undefined
82546 | [7 empty] | undefined
82547 | [7 empty] | undefined
83967 | [7 empty] | undefined
85738 | [7 empty] | undefined
85739 | [7 empty] | undefined
84283 | [7 empty] | undefined
84284 | [7 empty] | undefined
84285 | [7 empty] | undefined
97244 | [7 empty] | undefined
97349 | [7 empty] | undefined
97258 | [7 empty] | undefined
97260 | [7 empty] | undefined
97255 | [7 empty] | undefined
97257 | [7 empty] | undefined
84169 | [7 empty] | undefined
84381 | [7 empty] | undefined
84454 | [7 empty] | undefined
60152 | [7 empty] | undefined
60154 | [7 empty] | undefined
31414 | [7 empty] | undefined
31415 | [7 empty] | undefined
34592 | [7 empty] | undefined
35680 | [7 empty] | undefined
30657 | [7 empty] | undefined
12066 | [7 empty] | undefined
27537 | [7 empty] | undefined
28021 | [7 empty] | undefined
28022 | [7 empty] | undefined
28023 | [7 empty] | undefined
28024 | [7 empty] | undefined
28371 | [7 empty] | undefined
28453 | [7 empty] | undefined
46005 | [7 empty] | undefined
46035 | [7 empty] | undefined
53069 | [7 empty] | undefined
52490 | [7 empty] | undefined
48828 | [7 empty] | undefined
48798 | [7 empty] | undefined
47491 | [7 empty] | undefined
53801 | [7 empty] | undefined
55831 | [7 empty] | undefined
54754 | [7 empty] | undefined
67030 | [7 empty] | undefined
68486 | [7 empty] | undefined
64559 | [7 empty] | undefined
75648 | [7 empty] | undefined
61141 | [7 empty] | undefined
54268 | [7 empty] | undefined
54112 | [7 empty] | undefined
73075 | [7 empty] | undefined
73181 | [7 empty] | undefined
79675 | [7 empty] | undefined
79676 | [7 empty] | undefined
82294 | [7 empty] | undefined
85575 | [7 empty] | undefined
85305 | [7 empty] | undefined
84968 | [7 empty] | undefined
85730 | [7 empty] | undefined
85818 | [7 empty] | undefined
85999 | [7 empty] | undefined
86768 | [7 empty] | undefined
88228 | [7 empty] | undefined
88415 | [7 empty] | undefined
86769 | [7 empty] | undefined
88730 | [7 empty] | undefined
86800 | [7 empty] | undefined
89983 | [7 empty] | undefined
86803 | [7 empty] | undefined
86808 | [7 empty] | undefined
86866 | [7 empty] | undefined
86943 | [7 empty] | undefined
88787 | [7 empty] | undefined
88804 | [7 empty] | undefined
89132 | [7 empty] | undefined
88805 | [7 empty] | undefined
88389 | [7 empty] | undefined
88449 | [7 empty] | undefined
88639 | [7 empty] | undefined
88895 | [7 empty] | undefined
85588 | [7 empty] | undefined
85320 | [7 empty] | undefined
85332 | [7 empty] | undefined
85333 | [7 empty] | undefined
85660 | [7 empty] | undefined
85675 | [7 empty] | undefined
87829 | [7 empty] | undefined
89443 | [7 empty] | undefined
85593 | [7 empty] | undefined
84974 | [7 empty] | undefined
91762 | [7 empty] | undefined
91763 | [7 empty] | undefined
91764 | [7 empty] | undefined
91793 | [7 empty] | undefined
91897 | [7 empty] | undefined
88648 | [7 empty] | undefined
88650 | [7 empty] | undefined
88617 | [7 empty] | undefined
88670 | [7 empty] | undefined
88651 | [7 empty] | undefined
88675 | [7 empty] | undefined
88676 | [7 empty] | undefined
91984 | [7 empty] | undefined
91985 | [7 empty] | undefined
85581 | [7 empty] | undefined
85306 | [7 empty] | undefined
85698 | [7 empty] | undefined
85562 | [7 empty] | undefined
85689 | [7 empty] | undefined
86001 | [7 empty] | undefined
86002 | [7 empty] | undefined
86003 | [7 empty] | undefined
86005 | [7 empty] | undefined
86135 | [7 empty] | undefined
86136 | [7 empty] | undefined
86137 | [7 empty] | undefined
86538 | [7 empty] | undefined
86539 | [7 empty] | undefined
86540 | [7 empty] | undefined
86541 | [7 empty] | undefined
86567 | [7 empty] | undefined
86707 | [7 empty] | undefined
85690 | [7 empty] | undefined
85695 | [7 empty] | undefined
85696 | [7 empty] | undefined
85697 | [7 empty] | undefined
85701 | [7 empty] | undefined
87949 | [7 empty] | undefined
87950 | [7 empty] | undefined
86357 | [7 empty] | undefined
88604 | [7 empty] | undefined
86374 | [7 empty] | undefined
88789 | [7 empty] | undefined
86486 | [7 empty] | undefined
86676 | [7 empty] | undefined
87049 | [7 empty] | undefined
87559 | [7 empty] | undefined
87278 | [7 empty] | undefined
87592 | [7 empty] | undefined
87594 | [7 empty] | undefined
87866 | [7 empty] | undefined
88938 | [7 empty] | undefined
89665 | [7 empty] | undefined
89666 | [7 empty] | undefined
89442 | [7 empty] | undefined
85589 | [7 empty] | undefined
85567 | [7 empty] | undefined
85569 | [7 empty] | undefined
85570 | [7 empty] | undefined
85779 | [7 empty] | undefined
85780 | [7 empty] | undefined
85781 | [7 empty] | undefined
86121 | [7 empty] | undefined
86127 | [7 empty] | undefined
87011 | [7 empty] | undefined
87027 | [7 empty] | undefined
84453 | [7 empty] | undefined
87870 | [7 empty] | undefined
89441 | [7 empty] | undefined
88652 | [7 empty] | undefined
88658 | [7 empty] | undefined
88667 | [7 empty] | undefined
88671 | [7 empty] | undefined
88669 | [7 empty] | undefined
88672 | [7 empty] | undefined
88673 | [7 empty] | undefined
91982 | [7 empty] | undefined
91983 | [7 empty] | undefined
85590 | [7 empty] | undefined
85591 | [7 empty] | undefined
85331 | [7 empty] | undefined
85627 | [7 empty] | undefined
85776 | [7 empty] | undefined
85598 | [7 empty] | undefined
85596 | [7 empty] | undefined
85595 | [7 empty] | undefined
85629 | [7 empty] | undefined
85600 | [7 empty] | undefined
85601 | [7 empty] | undefined
85619 | [7 empty] | undefined
85620 | [7 empty] | undefined
85602 | [7 empty] | undefined
85603 | [7 empty] | undefined
85621 | [7 empty] | undefined
85604 | [7 empty] | undefined
85605 | [7 empty] | undefined
85606 | [7 empty] | undefined
85611 | [7 empty] | undefined
85623 | [7 empty] | undefined
85631 | [7 empty] | undefined
85633 | [7 empty] | undefined
85634 | [7 empty] | undefined
85635 | [7 empty] | undefined
85637 | [7 empty] | undefined
85639 | [7 empty] | undefined
85641 | [7 empty] | undefined
85642 | [7 empty] | undefined
85643 | [7 empty] | undefined
85644 | [7 empty] | undefined
85645 | [7 empty] | undefined
85646 | [7 empty] | undefined
85647 | [7 empty] | undefined
85648 | [7 empty] | undefined
85650 | [7 empty] | undefined
85768 | [7 empty] | undefined
85769 | [7 empty] | undefined
85770 | [7 empty] | undefined
85771 | [7 empty] | undefined
85772 | [7 empty] | undefined
85773 | [7 empty] | undefined
85774 | [7 empty] | undefined
85775 | [7 empty] | undefined
86124 | [7 empty] | undefined
86125 | [7 empty] | undefined
86122 | [7 empty] | undefined
86123 | [7 empty] | undefined
84515 | [7 empty] | undefined
86126 | [7 empty] | undefined
85835 | [7 empty] | undefined
86718 | [7 empty] | undefined
86720 | [7 empty] | undefined
86721 | [7 empty] | undefined
82046 | [7 empty] | undefined
72184 | [7 empty] | undefined
73010 | [7 empty] | undefined
73011 | [7 empty] | undefined
73013 | [7 empty] | undefined
73015 | [7 empty] | undefined
73016 | [7 empty] | undefined
73018 | [7 empty] | undefined
73019 | [7 empty] | undefined
73024 | [7 empty] | undefined
75130 | [7 empty] | undefined
75134 | [7 empty] | undefined
75380 | [7 empty] | undefined
91226 | [7 empty] | undefined
94417 | [7 empty] | undefined
95227 | [7 empty] | undefined
95239 | [7 empty] | undefined
86415 | [7 empty] | undefined
86425 | [7 empty] | undefined
82047 | [7 empty] | undefined
82050 | [7 empty] | undefined
89138 | [7 empty] | undefined
82051 | [7 empty] | undefined
84540 | [7 empty] | undefined
82052 | [7 empty] | undefined
82731 | [7 empty] | undefined
82049 | [7 empty] | undefined
82054 | [7 empty] | undefined
82055 | [7 empty] | undefined
82450 | [7 empty] | undefined
82451 | [7 empty] | undefined
85899 | [7 empty] | undefined
85900 | [7 empty] | undefined
86952 | [7 empty] | undefined
86953 | [7 empty] | undefined
81690 | [7 empty] | undefined
82425 | [7 empty] | undefined
82434 | [7 empty] | undefined
83109 | [7 empty] | undefined
83414 | [7 empty] | undefined
83415 | [7 empty] | undefined
83416 | [7 empty] | undefined
84433 | [7 empty] | undefined
84434 | [7 empty] | undefined
84461 | [7 empty] | undefined
84462 | [7 empty] | undefined
84463 | [7 empty] | undefined
84464 | [7 empty] | undefined
87831 | [7 empty] | undefined
87832 | [7 empty] | undefined
84377 | [7 empty] | undefined
93244 | [7 empty] | undefined
93225 | [7 empty] | undefined
94557 | [7 empty] | undefined
94559 | [7 empty] | undefined
94563 | [7 empty] | undefined
94652 | [7 empty] | undefined
94656 | [7 empty] | undefined
95219 | [7 empty] | undefined
95243 | [7 empty] | undefined
95244 | [7 empty] | undefined
95257 | [7 empty] | undefined
93232 | [7 empty] | undefined
94568 | [7 empty] | undefined
94569 | [7 empty] | undefined
93249 | [7 empty] | undefined
94553 | [7 empty] | undefined
94554 | [7 empty] | undefined
94556 | [7 empty] | undefined
94922 | [7 empty] | undefined
96698 | [7 empty] | undefined
97862 | [7 empty] | undefined
94389 | [7 empty] | undefined
94570 | [7 empty] | undefined
94571 | [7 empty] | undefined
94390 | [7 empty] | undefined
94572 | [7 empty] | undefined
94391 | [7 empty] | undefined
94573 | [7 empty] | undefined
94574 | [7 empty] | undefined
94575 | [7 empty] | undefined
94382 | [7 empty] | undefined
94383 | [7 empty] | undefined
94384 | [7 empty] | undefined
94386 | [7 empty] | undefined
94381 | [7 empty] | undefined
109173 | [7 empty] | undefined
109359 | [7 empty] | undefined
109360 | [7 empty] | undefined
109361 | [7 empty] | undefined
109362 | [7 empty] | undefined
109366 | [7 empty] | undefined
109374 | [7 empty] | undefined
109377 | [7 empty] | undefined
109378 | [7 empty] | undefined
109379 | [7 empty] | undefined
94387 | [7 empty] | undefined
94790 | [7 empty] | undefined
96602 | [7 empty] | undefined
96603 | [7 empty] | undefined
106903 | [7 empty] | undefined
109562 | [7 empty] | undefined
109563 | [7 empty] | undefined
110825 | [7 empty] | undefined
110826 | [7 empty] | undefined
106661 | [7 empty] | undefined
106662 | [7 empty] | undefined
94707 | [7 empty] | undefined
109387 | [7 empty] | undefined
109489 | [7 empty] | undefined
94714 | [7 empty] | undefined
109406 | [7 empty] | undefined
109407 | [7 empty] | undefined
109170 | [7 empty] | undefined
109393 | [7 empty] | undefined
109394 | [7 empty] | undefined
109171 | [7 empty] | undefined
109395 | [7 empty] | undefined
109396 | [7 empty] | undefined
109397 | [7 empty] | undefined
109398 | [7 empty] | undefined
109399 | [7 empty] | undefined
109401 | [7 empty] | undefined
109511 | [7 empty] | undefined
109172 | [7 empty] | undefined
109404 | [7 empty] | undefined
109480 | [7 empty] | undefined
109655 | [7 empty] | undefined
109734 | [7 empty] | undefined
110361 | [7 empty] | undefined
110364 | [7 empty] | undefined
111068 | [7 empty] | undefined
111069 | [7 empty] | undefined
111070 | [7 empty] | undefined
110366 | [7 empty] | undefined
110368 | [7 empty] | undefined
110369 | [7 empty] | undefined
110370 | [7 empty] | undefined
110371 | [7 empty] | undefined
110372 | [7 empty] | undefined
110711 | [7 empty] | undefined
111065 | [7 empty] | undefined
111066 | [7 empty] | undefined
111067 | [7 empty] | undefined
111071 | [7 empty] | undefined
110714 | [7 empty] | undefined
110362 | [7 empty] | undefined
110374 | [7 empty] | undefined
110378 | [7 empty] | undefined
110700 | [7 empty] | undefined
110703 | [7 empty] | undefined
110704 | [7 empty] | undefined
110705 | [7 empty] | undefined
110706 | [7 empty] | undefined
110707 | [7 empty] | undefined
110812 | [7 empty] | undefined
101496 | [7 empty] | undefined
109381 | [7 empty] | undefined
109386 | [7 empty] | undefined
109410 | [7 empty] | undefined
109412 | [7 empty] | undefined
109413 | [7 empty] | undefined
91308 | [7 empty] | undefined
78852 | [7 empty] | undefined
71669 | [7 empty] | undefined
92470 | [7 empty] | undefined
92471 | [7 empty] | undefined
92472 | [7 empty] | undefined
91322 | [7 empty] | undefined
91429 | [7 empty] | undefined
92350 | [7 empty] | undefined
91324 | [7 empty] | undefined
91436 | [7 empty] | undefined
91326 | [7 empty] | undefined
91515 | [7 empty] | undefined
91640 | [7 empty] | undefined
91641 | [7 empty] | undefined
91517 | [7 empty] | undefined
91730 | [7 empty] | undefined
91732 | [7 empty] | undefined
91733 | [7 empty] | undefined
91734 | [7 empty] | undefined
92030 | [7 empty] | undefined
91319 | [7 empty] | undefined
92238 | [7 empty] | undefined
92239 | [7 empty] | undefined
92240 | [7 empty] | undefined
91526 | [7 empty] | undefined
91527 | [7 empty] | undefined
92355 | [7 empty] | undefined
91565 | [7 empty] | undefined
93273 | [7 empty] | undefined
93274 | [7 empty] | undefined
93306 | [7 empty] | undefined
93335 | [7 empty] | undefined
92241 | [7 empty] | undefined
92242 | [7 empty] | undefined
92243 | [7 empty] | undefined
93598 | [7 empty] | undefined
93600 | [7 empty] | undefined
94614 | [7 empty] | undefined
94765 | [7 empty] | undefined
94812 | [7 empty] | undefined
93601 | [7 empty] | undefined
93602 | [7 empty] | undefined
93603 | [7 empty] | undefined
91305 | [7 empty] | undefined
91328 | [7 empty] | undefined
93388 | [7 empty] | undefined
91329 | [7 empty] | undefined
91331 | [7 empty] | undefined
92599 | [7 empty] | undefined
91332 | [7 empty] | undefined
91310 | [7 empty] | undefined
91551 | [7 empty] | undefined
89321 | [7 empty] | undefined
91311 | [7 empty] | undefined
89320 | [7 empty] | undefined
91312 | [7 empty] | undefined
91334 | [7 empty] | undefined
91335 | [7 empty] | undefined
91336 | [7 empty] | undefined
91337 | [7 empty] | undefined
93535 | [7 empty] | undefined
93961 | [7 empty] | undefined
91313 | [7 empty] | undefined
92109 | [7 empty] | undefined
93705 | [7 empty] | undefined
91314 | [7 empty] | undefined
91338 | [7 empty] | undefined
91339 | [7 empty] | undefined
91315 | [7 empty] | undefined
92233 | [7 empty] | undefined
92234 | [7 empty] | undefined
92235 | [7 empty] | undefined
92236 | [7 empty] | undefined
92237 | [7 empty] | undefined
91316 | [7 empty] | undefined
92264 | [7 empty] | undefined
92265 | [7 empty] | undefined
92266 | [7 empty] | undefined
92267 | [7 empty] | undefined
92268 | [7 empty] | undefined
92269 | [7 empty] | undefined
94171 | [7 empty] | undefined
94172 | [7 empty] | undefined
94949 | [7 empty] | undefined
94950 | [7 empty] | undefined
94952 | [7 empty] | undefined
95605 | [7 empty] | undefined
94175 | [7 empty] | undefined
94178 | [7 empty] | undefined
94180 | [7 empty] | undefined
94185 | [7 empty] | undefined
95661 | [7 empty] | undefined
95600 | [7 empty] | undefined
95601 | [7 empty] | undefined
97028 | [7 empty] | undefined
99435 | [7 empty] | undefined
97035 | [7 empty] | undefined
97036 | [7 empty] | undefined
97044 | [7 empty] | undefined
97046 | [7 empty] | undefined
97048 | [7 empty] | undefined
91318 | [7 empty] | undefined
92244 | [7 empty] | undefined
92245 | [7 empty] | undefined
92246 | [7 empty] | undefined
100175 | [7 empty] | undefined
100193 | [7 empty] | undefined
100194 | [7 empty] | undefined
101706 | [7 empty] | undefined
101798 | [7 empty] | undefined
101800 | [7 empty] | undefined
101801 | [7 empty] | undefined
101892 | [7 empty] | undefined
101893 | [7 empty] | undefined
101914 | [7 empty] | undefined
102001 | [7 empty] | undefined
101905 | [7 empty] | undefined
101917 | [7 empty] | undefined
102003 | [7 empty] | undefined
102832 | [7 empty] | undefined
102914 | [7 empty] | undefined
102025 | [7 empty] | undefined
102022 | [7 empty] | undefined
102023 | [7 empty] | undefined
102024 | [7 empty] | undefined
102998 | [7 empty] | undefined
102028 | [7 empty] | undefined
102030 | [7 empty] | undefined
102318 | [7 empty] | undefined
102031 | [7 empty] | undefined
102034 | [7 empty] | undefined
102039 | [7 empty] | undefined
102042 | [7 empty] | undefined
102006 | [7 empty] | undefined
102007 | [7 empty] | undefined
102043 | [7 empty] | undefined
102047 | [7 empty] | undefined
102049 | [7 empty] | undefined
102054 | [7 empty] | undefined
102055 | [7 empty] | undefined
103148 | [7 empty] | undefined
102344 | [7 empty] | undefined
102345 | [7 empty] | undefined
102534 | [7 empty] | undefined
101997 | [7 empty] | undefined
104095 | [7 empty] | undefined
104100 | [7 empty] | undefined
101998 | [7 empty] | undefined
104065 | [7 empty] | undefined
110042 | [7 empty] | undefined
102535 | [7 empty] | undefined
102320 | [7 empty] | undefined
103932 | [7 empty] | undefined
103133 | [7 empty] | undefined
103132 | [7 empty] | undefined
104060 | [7 empty] | undefined
103210 | [7 empty] | undefined
101804 | [7 empty] | undefined
101815 | [7 empty] | undefined
101821 | [7 empty] | undefined
102413 | [7 empty] | undefined
104655 | [7 empty] | undefined
104662 | [7 empty] | undefined
104694 | [7 empty] | undefined
104755 | [7 empty] | undefined
105455 | [7 empty] | undefined
105456 | [7 empty] | undefined
105457 | [7 empty] | undefined
105458 | [7 empty] | undefined
104809 | [7 empty] | undefined
104120 | [7 empty] | undefined
104136 | [7 empty] | undefined
104140 | [7 empty] | undefined
105020 | [7 empty] | undefined
105112 | [7 empty] | undefined
104121 | [7 empty] | undefined
104143 | [7 empty] | undefined
104908 | [7 empty] | undefined
104939 | [7 empty] | undefined
104940 | [7 empty] | undefined
105037 | [7 empty] | undefined
104122 | [7 empty] | undefined
104145 | [7 empty] | undefined
109061 | [7 empty] | undefined
104146 | [7 empty] | undefined
104147 | [7 empty] | undefined
104150 | [7 empty] | undefined
104790 | [7 empty] | undefined
104791 | [7 empty] | undefined
104792 | [7 empty] | undefined
104811 | [7 empty] | undefined
104992 | [7 empty] | undefined
105013 | [7 empty] | undefined
105042 | [7 empty] | undefined
105153 | [7 empty] | undefined
104538 | [7 empty] | undefined
109042 | [7 empty] | undefined
109046 | [7 empty] | undefined
104539 | [7 empty] | undefined
105160 | [7 empty] | undefined
109647 | [7 empty] | undefined
106541 | [7 empty] | undefined
106568 | [7 empty] | undefined
106583 | [7 empty] | undefined
106296 | [7 empty] | undefined
104123 | [7 empty] | undefined
104148 | [7 empty] | undefined
105043 | [7 empty] | undefined
105136 | [7 empty] | undefined
108958 | [7 empty] | undefined
106530 | [7 empty] | undefined
106378 | [7 empty] | undefined
104149 | [7 empty] | undefined
105146 | [7 empty] | undefined
105147 | [7 empty] | undefined
105148 | [7 empty] | undefined
106320 | [7 empty] | undefined
106329 | [7 empty] | undefined
106369 | [7 empty] | undefined
104569 | [7 empty] | undefined
105152 | [7 empty] | undefined
109646 | [7 empty] | undefined
106539 | [7 empty] | undefined
109002 | [7 empty] | undefined
106566 | [7 empty] | undefined
106577 | [7 empty] | undefined
106527 | [7 empty] | undefined
101805 | [7 empty] | undefined
101807 | [7 empty] | undefined
101816 | [7 empty] | undefined
101818 | [7 empty] | undefined
101912 | [7 empty] | undefined
103039 | [7 empty] | undefined
103040 | [7 empty] | undefined
103041 | [7 empty] | undefined
103042 | [7 empty] | undefined
103044 | [7 empty] | undefined
103045 | [7 empty] | undefined
101915 | [7 empty] | undefined
101925 | [7 empty] | undefined
102277 | [7 empty] | undefined
103035 | [7 empty] | undefined
103036 | [7 empty] | undefined
103037 | [7 empty] | undefined
104695 | [7 empty] | undefined
104696 | [7 empty] | undefined
106751 | [7 empty] | undefined
104703 | [7 empty] | undefined
104759 | [7 empty] | undefined
104777 | [7 empty] | undefined
104778 | [7 empty] | undefined
106954 | [7 empty] | undefined
106955 | [7 empty] | undefined
105159 | [7 empty] | undefined
109623 | [7 empty] | undefined
109630 | [7 empty] | undefined
106632 | [7 empty] | undefined
106636 | [7 empty] | undefined
106978 | [7 empty] | undefined
106979 | [7 empty] | undefined
109163 | [7 empty] | undefined
101918 | [7 empty] | undefined
101922 | [7 empty] | undefined
103676 | [7 empty] | undefined
101923 | [7 empty] | undefined
103669 | [7 empty] | undefined
103670 | [7 empty] | undefined
103355 | [7 empty] | undefined
103357 | [7 empty] | undefined
103366 | [7 empty] | undefined
103923 | [7 empty] | undefined
103082 | [7 empty] | undefined
103805 | [7 empty] | undefined
105090 | [7 empty] | undefined
105158 | [7 empty] | undefined
105174 | [7 empty] | undefined
105177 | [7 empty] | undefined
105178 | [7 empty] | undefined
109408 | [7 empty] | undefined
109509 | [7 empty] | undefined
110260 | [7 empty] | undefined
110348 | [7 empty] | undefined
110349 | [7 empty] | undefined
109481 | [7 empty] | undefined
110687 | [7 empty] | undefined
106519 | [7 empty] | undefined
101919 | [7 empty] | undefined
101930 | [7 empty] | undefined
104083 | [7 empty] | undefined
104131 | [7 empty] | undefined
103807 | [7 empty] | undefined
103808 | [7 empty] | undefined
101935 | [7 empty] | undefined
103806 | [7 empty] | undefined
103085 | [7 empty] | undefined
103839 | [7 empty] | undefined
105114 | [7 empty] | undefined
105116 | [7 empty] | undefined
109151 | [7 empty] | undefined
109357 | [7 empty] | undefined
105321 | [7 empty] | undefined
109500 | [7 empty] | undefined
110798 | [7 empty] | undefined
110800 | [7 empty] | undefined
109530 | [7 empty] | undefined
109531 | [7 empty] | undefined
110683 | [7 empty] | undefined
110686 | [7 empty] | undefined
101920 | [7 empty] | undefined
101938 | [7 empty] | undefined
110681 | [7 empty] | undefined
110684 | [7 empty] | undefined
110732 | [7 empty] | undefined
101921 | [7 empty] | undefined
101940 | [7 empty] | undefined
104118 | [7 empty] | undefined
104231 | [7 empty] | undefined
109169 | [7 empty] | undefined
110330 | [7 empty] | undefined
110351 | [7 empty] | undefined
103952 | [7 empty] | undefined
103996 | [7 empty] | undefined
103997 | [7 empty] | undefined
104006 | [7 empty] | undefined
104058 | [7 empty] | undefined
93224 | [7 empty] | undefined
93917 | [7 empty] | undefined
93918 | [7 empty] | undefined
93920 | [7 empty] | undefined
99796 | [7 empty] | undefined
99797 | [7 empty] | undefined
99798 | [7 empty] | undefined
104399 | [7 empty] | undefined
104400 | [7 empty] | undefined
104453 | [7 empty] | undefined
104546 | [7 empty] | undefined
104430 | [7 empty] | undefined
104549 | [7 empty] | undefined
104550 | [7 empty] | undefined
109466 | [7 empty] | undefined
110256 | [7 empty] | undefined
104568 | [7 empty] | undefined
105570 | [7 empty] | undefined
105632 | [7 empty] | undefined
104628 | [7 empty] | undefined
110669 | [7 empty] | undefined
104565 | [7 empty] | undefined
104567 | [7 empty] | undefined
104555 | [7 empty] | undefined
104556 | [7 empty] | undefined
105382 | [7 empty] | undefined
109703 | [7 empty] | undefined
109706 | [7 empty] | undefined
109755 | [7 empty] | undefined
110833 | [7 empty] | undefined
110834 | [7 empty] | undefined
110840 | [7 empty] | undefined
110841 | [7 empty] | undefined
110843 | [7 empty] | undefined
110989 | [7 empty] | undefined
106670 | [7 empty] | undefined
106671 | [7 empty] | undefined
106672 | [7 empty] | undefined
104559 | [7 empty] | undefined
110512 | [7 empty] | undefined
110513 | [7 empty] | undefined
110514 | [7 empty] | undefined
110710 | [7 empty] | undefined
100888 | [7 empty] | undefined
110498 | [7 empty] | undefined
110499 | [7 empty] | undefined
110500 | [7 empty] | undefined
110501 | [7 empty] | undefined
110502 | [7 empty] | undefined
110503 | [7 empty] | undefined
110504 | [7 empty] | undefined
110505 | [7 empty] | undefined
110506 | [7 empty] | undefined
110507 | [7 empty] | undefined
110508 | [7 empty] | undefined
110511 | [7 empty] | undefined
110509 | [7 empty] | undefined
110510 | [7 empty] | undefined
110709 | [7 empty] | undefined
110515 | [7 empty] | undefined
110516 | [7 empty] | undefined
105130 | [7 empty] | undefined
105131 | [7 empty] | undefined
105142 | [7 empty] | undefined
105161 | [7 empty] | undefined
105162 | [7 empty] | undefined
105167 | [7 empty] | undefined
105144 | [7 empty] | undefined
105145 | [7 empty] | undefined
105156 | [7 empty] | undefined
103248 | [7 empty] | undefined
78622 | [7 empty] | undefined
78630 | [7 empty] | undefined
78631 | [7 empty] | undefined
99493 | [7 empty] | undefined
103914 | [7 empty] | undefined
103920 | [7 empty] | undefined
102017 | [7 empty] | undefined
102411 | [7 empty] | undefined
102906 | [7 empty] | undefined
102909 | [7 empty] | undefined
102912 | [7 empty] | undefined
102938 | [7 empty] | undefined
102987 | [7 empty] | undefined
103175 | [7 empty] | undefined
103699 | [7 empty] | undefined
103214 | [7 empty] | undefined
103816 | [7 empty] | undefined
109704 | [7 empty] | undefined
109707 | [7 empty] | undefined
109765 | [7 empty] | undefined
109766 | [7 empty] | undefined
109767 | [7 empty] | undefined
110036 | [7 empty] | undefined
110227 | [7 empty] | undefined
110228 | [7 empty] | undefined
110229 | [7 empty] | undefined
106643 | [7 empty] | undefined
109705 | [7 empty] | undefined
109708 | [7 empty] | undefined
110225 | [7 empty] | undefined
106681 | [7 empty] | undefined
106682 | [7 empty] | undefined
109675 | [7 empty] | undefined
110824 | [7 empty] | undefined
110827 | [7 empty] | undefined
110830 | [7 empty] | undefined
106683 | [7 empty] | undefined
106823 | [7 empty] | undefined
106824 | [7 empty] | undefined